## Main
Scrum Project
Sprint Plan
| Sprint | Start | End | Status | Work planned (Committed) | Work spent (Delivered) | Remarks
| 1 | September 8,2025 | September 28,2025 | Complete | 355 | 413
| 2 | October 6, 2025 | October 26, 2025 | Complete | 356 | 411
| 3 | November 3, 2025 | November 23, 2025 | Complete | 338 | 370

## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Sign up |  | register a new account | access LeafSense features | Sign up validates required fields and unique email; password policy is enforced; successful submission confirms and creates an account; error messages are clear and user-friendly |  | 1 |  |  |  | 1 | 20
PB02 | Log in |  | log in to my account | secure system access | Valid credentials grant access; invalid blocked with message; session created; redirects tohome/dashboard |  | 1 |  |  |  | 1 | 20
PB03 | Log out |  | log out of my account | keep your account safe | The login session is deleted and the user is securely logged out. |  | 2 |  |  |  | 1 | 20
PB04 | Forgot password |  | reset my password | regain secure access | Password reset email sent and updated successfully |  | 2 |  |  |  | 1 | 25
PB05 | Home page interface(Admin) | [5 empty] | 2 |  |  |  | 1 | 25
PB06 | Home page interface(Supermarket Admin)
PB07 | Home page interface(Staff)
PB08 | Home page interface(Charity)
PB09 | Home page interface(Customer)
PB10 | Home page interface(Delivery)
PB11 | View profile(Admin) | [5 empty] | 2 |  |  |  | 1 | 20
PB12 | View profile(Supermarket Admin) |  | view personal information | account information management | Shows name/email/phone/avatar; data matches DB; no sensitive fields (password) |  | 3 |  |  |  | 1 | 30
PB13 | View profile(Staff) |  | view personal information | account information management | Shows name/email/role; data matches DB; no sensitive data (password) exposed. |  | 3 |  |  |  | 1 | 30
PB14 | View profile(Charity) | [5 empty] | 1 |  |  |  | 1 | 40
PB15 | View profile(Customer) | [5 empty] | 1 |  |  |  | 1 | 10
PB16 | View profile(Delivery)
PB17 | Edit profile(Admin)
PB18 | Edit profile(Supermarket Admin)
PB19 | Edit profile(Staff)
PB20 | Edit profile(Charity)
PB21 | Edit profile(Customer)
PB22 | Edit profile(Delivery)
PB17 | Supermarket manager |  | delete farmer's account | maintain access control | Delete requires confirmation; account disabled/removed; user cannot log in; deletion event logged |  | 1 |  |  |  | 2 | 25
PB18 | Charity organization management
PB19 | Delivery management
PB20 | User management
PB21 | Store management
PB22 | Store staff management
PB23 | Policy configuration
PB24 | Monitoring donations
PB37 | Category management |  | add, edit, delete categories | clear organization | CRUD list works properly, save DB successfully |  | 2 |  |  |  | 2 | 25
PB38 | Product management |  | add, edit, delete products, update prices and inventory | ensure accurate data | Create/update/delete with required fields (name, price, stock); updates visible immediately;negative price/stock blocked |  | 1 |  |  |  | 2 | 25
PB24
PB25
PB26
PB27
PB28
PB29
PB30
PB31
PB32 | [6 empty] | 1 |  |  |  | 2 | 20
PB33 | [6 empty] | 1 |  |  |  | 2 | 15
PB35 | [6 empty] | 2 |  |  |  | 2 | 20
PB36 | Firebase Integration |  | to securely store uploaded images and retrieve them quickly via Firebase | image access is fast, reliable, and URLs can be safely reused across the application | Images are uploaded successfully to Firebase Storage;A download URL is generated after upload;The image URL is saved in the database;The saved URL can be retrieved and used to display the image;Image access is fast and does not fail on page reload |  | 1 |  |  |  | 2 | 5
PB37 | Category Management |  | add, edit, delete categories | clear organization | CRUD list works properly, save DB successfully |  | 2 |  |  |  | 2 | 25
PB38 | Product Management |  | add, edit, delete products, update prices and inventory | ensure accurate data | Create/update/delete with required fields (name, price, stock); updates visible immediately;negative price/stock blocked |  | 1 |  |  |  | 2 | 25
PB39 | Online marketplace |  | browse product list | select agricultural supplies to buy | Product grid/list loads with name/price/stock; filters/sort work; performance acceptable (<3s) |  | 1 |  |  |  | 2 | 25
PB40 | Search & Filter Products |  | find products by name, category | fast and accurate search | Search by keyword; filter by category; results relevant and up to date |  | 2 |  |  |  | 2 | 20
PB41 | Shopping cart |  | add, remove or update products in the cart | manage products you want to buy before checking out | Add/remove/update quantity; totals recalc immediately; prevents negative/over-stock quantities |  | 1 |  |  |  | 2 | 25
PB42 | Coupon Management |  | create, edit, delete, and manage coupon codes | run a discount program in the marketplace | Create/update/disable codes; configure value, expiry, conditions; expired codes unusable; discount calculated correctly. |  | 2 |  |  |  | 2 | 25
PB43 | Apply coupon code at checkout |  | enter the discount code during checkout | get a discount when paying for an order | Valid code applies correct discount; expired/invalid blocked with message; cannot stack unsupported combos |  | 2 |  |  |  | 2 | 20
PB27 | Checkout |  | review order and confirm payment | complete my purchase process | Order summary shows items/price/discount/shipping/address; confirmation recordsorder and status; errors are clear |  | 1 |  |  |  | 3 | 25
PB28 | Enter delivery location using Google Map |  | select delivery address on map | ensure accurate delivery | Map loads; can pick/search address; address saved with order; validation prevents empty/invalid |  | 1 |  |  |  | 2 | 15
PB29 | COD payment |  | choose cash on delivery | pay after receiving the goods successfully | COD option selectable; fee (if any) shown; order stored with COD status; instructions shown |  | 1 |  |  |  | 3 | 10
PB30 | MoMo Payment |  | payment by MoMo wallet | complete transactions quickly | MoMo option available; successful payment updates order to paid; failures show error and order stays unpaid; receipt stored |  | 1 |  |  |  | 3 | 20
PB32 | Order management |  | view and update orders | ensure on-time delivery | See orders with statuses; can set pending/shipping/completed/cancelled; changes persist and visible to customers; status changes logged |  | 1 |  |  |  | 3 | 20
PB33 | Order history |  | view my previous orders | track status and payments | Order list with status, totals, payment method; can open details; pagination works. |  | 2 |  |  |  | 3 | 25
PB34 | [6 empty] | 2 |  |  |  | 3 | 20
PB35 | [6 empty] | 2 |  |  |  | 3 | 25
PB36 | [6 empty] | 1 |  |  |  | 3 | 25
PB37 | [6 empty] | 2 |  |  |  | 3 | 25
PB38 | Dashboard(Admin) |  | view system statistics | monitor user activity, posts, orders | Dashboard shows user/post/order counts and revenue summary; loads <3s; admin-only access |  | 1 |  |  |  | 3 | 20
Dashboard(Supermarket Admin)
Dashboard(Staff)
Dashboard(Charity)
Dashboard(Customer)
PB39 | Dashboard(Delivery) |  | view personal activity overview | easily manage my activities | Dashboard shows recent analyses, orders, posts, and notifications; loads <3s; links navigate to details. |  | 1 |  |  |  | 3 | 20
PB40 | Lock/Unlock User Account |  | lock or unlock farmer's account | restrict users who violate community rules or system policies | Lock/unlock works; locked users cannot log in; status shown to user; action logged |  | 1 |  |  |  | 3 | 20
Note on M7: ====== ID#AAABuu-MR1k (2025-12-07 14:55:26) Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.
Note on N7: ====== ID#AAABuu-MR10 jan samuelsson (2025-12-07 14:55:26) Just rough numbers, 5,10,15,20 etc. Not 7, 13, 21 etc.

## Sprint 1 Backlog
Sprint 1 Backlog
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
1,1 |  | Sprint Detail Plan | Binh | Done | 5 | 5 | 0 | 5 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,2 |  | Planning meeting | All member | Done | 5 | 5 | 0 | 5 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,3 |  | Create Proposal Document | Thang | Done | 6 | 6 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,4 |  | Create Project Plan Document | Trang | Done | 5 | 3 | 2 | 5 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,5 |  | Create Product Backlog Document | Thang | Done | 6 | 6 | 0 | 5 | -1 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,6 |  | Create User Story Document | Bao | Done | 5 | 7 | -2 | 8 | 3 | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,7 |  | Create Database Design Document | Huy | Done | 10 | 10 | 0 | 15 | 5 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,8 |  | Create Interface Design Document | Bao | Done | 10 | 10 | 0 | 12 | 2 | 0 | 0 | 2 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,9 |  | Create Architecture Design Document | Binh | Done | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,10 |  | Create Sprint 1 Backlog | Huy | Done | 5 | 5 | 0 | 8 | 3 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,11 |  | Create Test Plan for Sprint 1 | Thang | Done | 2 | 3 | -1 | 5 | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,12 |  | Create Test Case for Sprint 1 | Thang | Done | 3 | 3 | 0 | 5 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,13 |  | Create Database | Bao | Done | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,14 | PB01 | [Design]Sign up | Trang | Done | 5 | 5 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,15 | PB02 | [Design]Log in | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,16 | PB03 | [Design]Sign in with Google | Trang | Done | 5 | 6 | -1 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,17 | PB06 | [Design]Home page interface(Farmer) | Trang | Done | 5 | 5 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,18 | PB07 | [Design]Home page interface(Admin) | Trang | Done | 5 | 5 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,19 | PB04 | [Design]Log out | Trang | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,20 | PB05 | [Design]Forgot password | Trang | Done | 5 | 5 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,21 | PB08 | [Design]View profile(Farmer) | Binh | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,22 | PB09 | [Design]View profile(Admin) | Binh | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,23 | PB10 | Collect dataset | All member | Done | 40 | 40 | 0 | 50 | 10 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,24 | PB11 | Train AI | All member | Done | 10 | 10 | 0 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1,25 | PB01 | [FE]Sign up | Huy | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,26 | PB01 | [BE]Sign up | Huy | Done | 5 | 6 | -1 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1,27 | PB02 | [FE]Log in | Bao | Done | 8 | 12 | -4 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
1,28 | PB02 | [BE]Log in | Bao | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
1,29 | PB03 | [FE]Sign in with Google | Huy | Done | 10 | 10 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
1,30 | PB03 | [BE]Sign in with Google | Huy | Done | 8 | 8 | 0 | 7 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0
1,31 | PB06 | [FE]Home page interface(Farmer) | Trang | Done | 8 | 8 | 0 | 7 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1,32 | PB06 | [BE]Home page interface(Farmer) | Trang | Done | 10 | 10 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 2 | 2 | 0 | 0 | 0
1,33 | PB07 | [FE]Home page interface(Admin) | Binh | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,34 | PB07 | [BE]Home page interface(Admin) | Binh | Done | 5 | 5 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
1,35 | PB04 | [FE]Log out | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0
1,36 | PB04 | [BE]Log out | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
1,37 | PB05 | [FE]Forgot password | Huy | Done | 5 | 5 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
1,38 | PB05 | [BE]Forgot password | Huy | Done | 10 | 10 | 0 | 5 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0
1,39 | PB08 | [FE]View profile(Farmer) | Thang | Done | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0
1,40 | PB08 | [BE]View profile(Farmer) | Thang | Done | 10 | 8 | 2 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0
1,41 | PB09 | [FE]View profile(Admin) | Binh | Done | 10 | 10 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 0 | 0
1,42 | PB09 | [BE]View profile(Admin) | Binh | Done | 10 | 8 | 2 | 8 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 0 | 0
1,43 | PB01 | [Test]Sign up | Thang | Done | 2 | 3 | -1 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
1,44 | PB02 | [Test]Log in | Huy | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
1,45 | PB03 | [Test]Sign in with Google | Thang | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
1,46 | PB04 | [Test]Log out | Thang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 0
1,47 | PB05 | [Test]Forgot password | Binh | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,48 | PB06 | [Test]Home page interface(Farmer) | Thang | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
1,49 | PB07 | [Test]Home page interface(Admin) | Thang | Done | 2 | 3 | -1 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
1,50 | PB08 | [Test]View profile(Farmer) | Bao | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,51 | PB09 | [Test]View profile(Admin) | Bao | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0
1,52 |  | Sprint 1 Review Meeting | All member | Done | 4 | 5 | -1 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
1,53 |  | Sprint 1 Retrospective | All member | Done | 4 | 5 | -1 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  |  |  | Total | 355 | 360 | -5 | 413 | 58 | 9 | 15 | 18 | 15 | 16 | 15 | 20 | 19 | 15 | 20 | 24 | 22 | 20 | 19 | 22 | 22 | 18 | 11 | 16 | 14 | 10
|  |  |  | Burn down | [5 empty] | 404 | 389 | 371 | 356 | 340 | 325 | 305 | 286 | 271 | 251 | 227 | 205 | 185 | 166 | 144 | 122 | 104 | 93 | 77 | 63 | 53
|  |  |  | Burn up | [5 empty] | 9 | 24 | 42 | 57 | 73 | 88 | 108 | 127 | 142 | 162 | 186 | 208 | 228 | 247 | 269 | 291 | 309 | 320 | 336 | 350 | 360
|  |  |  | Hour/Day | 17.1429
|  |  |  | Estimate |  |  |  |  | 413 | 395.8571 | 378.7143 | 361.5714 | 344.4286 | 327.2857 | 310.1429 | 293 | 275.8571 | 258.7143 | 241.5714 | 224.4286 | 207.2857 | 190.1429 | 173 | 155.8571 | 138.7143 | 121.5714 | 104.4286 | 87.2857 | 70.1429 | 53 | 0
|  |  |  | Actual |  |  |  |  | 413 | 404 | 389 | 371 | 356 | 340 | 325 | 305 | 286 | 271 | 251 | 227 | 205 | 185 | 166 | 144 | 122 | 104 | 93 | 77 | 63 | 53 | 0
[9 empty] | Trang | 0 | 1 | 1 | 1 | 0 | 2 | 5 | 6 | 6 | 6 | 9 | 5 | 5 | 6 | 5 | 5 | 3 | 2 | 0 | 0 | 1 | 69
[9 empty] | Huy | 0 | 1 | 1 | 2 | 3 | 1 | 3 | 2 | 2 | 4 | 7 | 7 | 5 | 6 | 7 | 6 | 5 | 0 | 1 | 1 | 1 | 65
[9 empty] | Thang | 2 | 4 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 4 | 4 | 5 | 5 | 5 | 6 | 1 | 52
[9 empty] | Binh | 1 | 2 | 2 | 2 | 2 | 3 | 4 | 3 | 1 | 3 | 3 | 4 | 5 | 3 | 2 | 4 | 4 | 4 | 6 | 2 | 1 | 61
[9 empty] | Bao | 0 | 2 | 4 | 2 | 5 | 4 | 4 | 4 | 2 | 2 | 3 | 3 | 1 | 2 | 2 | 3 | 1 | 0 | 4 | 5 | 1 | 54
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart

## Sprint 2 Backlog
Sprint 2 Backlog
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
1,1 |  | Sprint Detail Plan | All member | Done | 8 | 8 | 0 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,2 |  | Planning Meeting | All member | Done | 5 | 5 | 0 | 6 | 1 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,3 |  | Update Database Design Document | Huy | Done | 8 | 8 | 0 | 10 | 2 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,4 |  | Update Interface Design Document | Bao | Done | 8 | 8 | 0 | 6 | -2 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,5 |  | Create Sprint 2 Backlog | Huy | Done | 5 | 5 | 0 | 5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,6 |  | Create Test Plan for Sprint 2 | Huy | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,7 |  | Create Test Case for Sprint 2 | Binh | Done | 10 | 12 | -2 | 14 | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,8 |  | Update Database | Huy,Bao | Done | 10 | 10 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,9 | PB12 | [Design]User Management | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,10 | PB13 | [Design]Upload image | Trang | Done | 5 | 8 | -3 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,11 | PB14 | [Design]View analysis results | Trang | Done | 3 | 3 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,12 | PB15 | [Design]Treatment recommendations | Trang | Done | 3 | 5 | -2 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,13 | PB16 | [Design]History analysis | Trang | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,14 | PB18 | [Design]Category Management | Trang | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,15 | PB19 | [Design]Product Management | Trang | Done | 5 | 6 | -1 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,16 | PB20 | [Design]Online marketplace | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,17 | PB21 | [Design]Search & Filter Products | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,18 | PB22 | [Design]Shopping cart | Trang | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,20 | PB23 | [Design]Coupon Management | Trang | Done | 3 | 5 | -2 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,21 | PB24 | [Design]Apply coupon code at checkout | Trang | Done | 5 | 6 | -1 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1,22 | PB12 | [FE]User Management | Trang | Done | 10 | 10 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,23 | PB12 | [BE]User Management | Trang | Done | 8 | 8 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1,24 | PB13 | [FE]Upload image | Huy | Done | 5 | 5 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1,25 | PB13 | [BE]Upload image | Huy | Done | 5 | 5 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
1,26 | PB14 | [FE]View analysis results | Huy | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,27 | PB14 | [BE]View analysis results | Huy | Done | 5 | 6 | -1 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1,28 | PB15 | [FE]Treatment recommendations | Huy | Done | 5 | 5 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1,29 | PB15 | [BE]Treatment recommendations | Huy | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
1,30 | PB16 | [FE]History analysis | Huy | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
1,31 | PB16 | [BE]History analysis | Huy | Done | 8 | 10 | -2 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
1,32 | PB17 | [BE]Firebase Integration | Huy | Done | 3 | 5 | -2 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,33 | PB18 | [FE]Category Management | Thang | Done | 10 | 10 | 0 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
1,34 | PB18 | [BE]Category Management | Thang | Done | 8 | 10 | -2 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
1,35 | PB19 | [FE]Product Management | Thang | Done | 10 | 10 | 0 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,36 | PB19 | [BE]Product Management | Thang | Done | 7 | 7 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1,37 | PB20 | [FE]Online marketplace | Bao | Done | 8 | 8 | 0 | 6 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
1,38 | PB20 | [BE]Online marketplace | Bao | Done | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0
1,39 | PB21 | [FE]Search & Filter Products | Thang | Done | 7 | 7 | 0 | 5 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0
1,40 | PB21 | [BE]Search & Filter Products | Thang | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0
1,41 | PB22 | [FE]Shopping cart | Bao | Done | 8 | 8 | 0 | 7 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
1,42 | PB22 | [BE]Shopping cart | Bao | Done | 10 | 8 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0
1,45 | PB23 | [FE]Coupon Management | Binh | Done | 7 | 7 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 0 | 0 | 0
1,46 | PB23 | [BE]Coupon Management | Binh | Done | 10 | 10 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 2 | 3 | 0 | 0
1,47 | PB24 | [FE]Apply coupon code at checkout | Bao | Done | 8 | 8 | 0 | 5 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 2 | 0 | 0
1,48 | PB24 | [BE]Apply coupon code at checkout | Bao | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 1 | 0 | 0
1,49 | PB25 | [BE]Edit profile(Farmer) | Thang | Done | 10 | 10 | 0 | 9 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 2 | 2 | 3 | 0 | 0 | 0
1,50 | PB25 | [BE]Edit profile(Admin) | Thang | Done | 10 | 8 | 2 | 8 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 2 | 0 | 0 | 0
1,51 | PB12 | [Test]User Management | Binh | Done | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0
1,52 | PB13 | [Test]Upload image | Binh | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0
1,53 | PB14 | [Test]View analysis results | Binh | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
1,54 | PB15 | [Test]Treatment recommendations | Binh | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
1,55 | PB16 | [Test]History analysis | Binh | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1,56 | PB17 | [Test]Firebase Integration | Huy | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
1,57 | PB18 | [Test]Category Management | Binh | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1,58 | PB19 | [Test]Product Management | Binh | Done | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
1,59 | PB20 | [Test]Online marketplace | Binh | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
1,60 | PB21 | [Test]Search & Filter Products | Binh | Done | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0
1,61 | PB22 | [Test]Shopping cart | Binh | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
1,63 | PB23 | [Test]Coupon Management | Binh | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
1,64 | PB24 | [Test]Apply coupon code at checkout | Binh | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
1,65 | PB25 | [Test]Edit profile(Farmer) | Binh | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
1,66 | PB26 | [Test]Edit profile(Admin) | Binh | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
1,67 |  | Sprint 2 Review Meeting | All member | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
1,68 |  | Sprint 2 Retrospective | All member | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  |  |  | Total | 356 | 369 | -13 | 411 | 55 | 4 | 7 | 11 | 10 | 8 | 14 | 12 | 12 | 10 | 12 | 16 | 23 | 27 | 31 | 37 | 33 | 29 | 28 | 18 | 9 | 10
|  |  |  | Burn down | [5 empty] | 407 | 400 | 389 | 379 | 371 | 357 | 345 | 333 | 323 | 311 | 295 | 272 | 245 | 214 | 177 | 144 | 115 | 87 | 69 | 60 | 50
|  |  |  | Burn up | [5 empty] | 4 | 11 | 22 | 32 | 40 | 54 | 66 | 78 | 88 | 100 | 116 | 139 | 166 | 197 | 234 | 267 | 296 | 324 | 342 | 351 | 361
|  |  |  | Hour/Day | 17.5714
|  |  |  | Estimate |  |  |  |  | 411 | 389.4286 | 371.8571 | 354.2857 | 336.7143 | 319.1429 | 301.5714 | 284 | 266.4286 | 248.8571 | 231.2857 | 213.7143 | 196.1429 | 178.5714 | 161 | 143.4286 | 125.8571 | 108.2857 | 90.7143 | 73.1429 | 55.5714 | 38 | 0
|  |  |  | Actual |  |  |  |  | 411 | 407 | 400 | 389 | 379 | 371 | 357 | 345 | 333 | 323 | 311 | 295 | 272 | 245 | 214 | 177 | 144 | 115 | 87 | 69 | 60 | 50 | 0
[9 empty] | Trang | 0 | 0 | 0 | 0 | 1 | 7 | 8 | 10 | 8 | 9 | 8 | 10 | 9 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 82
[9 empty] | Huy | 0 | 1 | 6 | 6 | 4 | 4 | 3 | 2 | 2 | 1 | 4 | 8 | 8 | 10 | 9 | 6 | 2 | 0 | 0 | 0 | 1 | 77
[9 empty] | Thang | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 10 | 10 | 10 | 9 | 8 | 8 | 1 | 0 | 1 | 68
[9 empty] | Binh | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 9 | 10 | 10 | 9 | 1 | 56
[9 empty] | Bao | 0 | 0 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 4 | 10 | 10 | 10 | 10 | 7 | 0 | 1 | 70
Note on B7: ====== ID#AAABuu-MR14 jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAABuu-MR1s jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 2 Reports
Reports & Dashboards
Burn down Chart

## Sprint 3 Backlog
Sprint 3 Backlog
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
1,1 |  | Sprint Detail Plan | All member | Done | 5 | 5 | 0 | 6 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,2 |  | Planning Meeting | Huy | Done | 5 | 5 | 0 | 5 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,3 |  | Update Database Design Document | Huy | Done | 8 | 8 | 0 | 10 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,4 |  | Update Interface Design Document | Bao | Done | 8 | 8 | 0 | 6 | -2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,5 |  | Create Sprint 3 Backlog | Huy | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,6 |  | Create Test Plan for Sprint 3 | Thang | Done | 3 | 3 | 0 | 4 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,7 |  | Create Test Case for Sprint 3 | Binh | Done | 3 | 3 | 0 | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,8 | PB27 | [Design]Checkout | Trang | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,9 | PB28 | [Design]Enter delivery location using Google Map | Trang | Not Started | 5 | 0 | 5 | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,10 | PB30 | [Design]MoMo Payment | Trang | Done | 4 | 4 | 0 | 6 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,11 | PB31 | [Design]Product Reviews | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,12 | PB32 | [Design]Order management | Trang | Done | 3 | 5 | -2 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,13 | PB33 | [Design]Order history | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,14 | PB34 | [Design]Community posts | Trang | Done | 5 | 6 | -1 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,15 | PB35 | [Design]Comments & Reactions | Trang | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,16 | PB36 | [Design]Community Management | Trang | Done | 5 | 7 | -2 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,17 | PB37 | [Design]Q&A Chatbot | Trang | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,18 | PB38 | [Design]Dashboard(Admin) | Trang | Done | 5 | 6 | -1 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,19 | PB39 | [Design]Dashboard(Farmer) | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,20 | PB40 | [Design]Lock/Unlock User Account | Trang | Done | 5 | 6 | -1 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,21 | PB27 | [FE]Checkout | Bao | Done | 10 | 10 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,22 | PB27 | [BE]Checkout | Bao | Done | 5 | 6 | -1 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,23 | PB28 | [FE]Enter delivery location using Google Map | Huy | Not Started | 5 | 0 | 5 | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,24 | PB28 | [BE]Enter delivery location using Google Map | Huy | Not Started | 3 | 0 | 3 | 0 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,25 | PB29 | [BE]COD payment | Bao | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,26 | PB30 | [FE]MoMo Payment | Bao | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,27 | PB30 | [BE]MoMo Payment | Bao | Done | 5 | 5 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,28 | PB31 | [FE]Product Reviews | Bao | Done | 10 | 10 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,29 | PB31 | [BE]Product Reviews | Bao | Done | 7 | 7 | 0 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1,30 | PB32 | [FE]Order management | Binh | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,31 | PB32 | [BE]Order management | Binh | Done | 4 | 4 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0
1,32 | PB33 | [FE]Order history | Binh | Done | 8 | 10 | -2 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0
1,33 | PB33 | [BE]Order history | Binh | Done | 8 | 10 | -2 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
1,34 | PB34 | [FE]Community posts | Thang | Done | 7 | 7 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0
1,35 | PB34 | [BE]Community posts | Thang | Done | 6 | 8 | -2 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
1,36 | PB35 | [FE]Comments & Reactions | Thang | Done | 10 | 10 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
1,37 | PB35 | [BE]Comments & Reactions | Thang | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
1,38 | PB36 | [FE]Community Management | Thang | Done | 8 | 8 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0
1,39 | PB36 | [BE]Community Management | Thang | Done | 10 | 10 | 0 | 6 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0
1,40 | PB37 | [FE]Q&A Chatbot | Binh | Done | 10 | 10 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
1,41 | PB37 | [BE]Q&A Chatbot | Binh | Done | 8 | 8 | 0 | 7 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0
1,42 | PB38 | [FE]Dashboard(Admin) | Huy | Done | 6 | 6 | 0 | 5 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0
1,43 | PB38 | [BE]Dashboard(Admin) | Huy | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0
1,44 | PB39 | [FE]Dashboard(Farmer) | Huy | Done | 8 | 7 | 1 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0
1,45 | PB39 | [BE]Dashboard(Farmer) | Huy | Done | 5 | 5 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0
1,46 | PB40 | [FE]Lock/Unlock User Account | Huy | Done | 6 | 6 | 0 | 5 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0
1,47 | PB40 | [BE]Lock/Unlock User Account | Huy | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
1,48 | PB27 | [Test]Checkout | Bao | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,49 | PB28 | [Test]Enter delivery location using Google Map | Bao | Not Started | 2 | 0 | 2 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,50 | PB29 | [Test]COD payment | Bao | Done | 5 | 4 | 1 | 3 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,51 | PB30 | [Test]MoMo Payment | Bao | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
1,52 | PB31 | [Test]Product Reviews | Binh | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
1,53 | PB32 | [Test]Order management | Binh | Done | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
1,54 | PB33 | [Test]Order history | Binh | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
1,55 | PB34 | [Test]Community posts | Thang | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
1,56 | PB35 | [Test]Comments & Reactions | Thang | Done | 5 | 4 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1
1,57 | PB36 | [Test]Community Management | Thang | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
1,58 | PB37 | [Test]Q&A Chatbot | Binh | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
1,59 | PB38 | [Test]Dashboard(Admin) | Huy | Done | 5 | 4 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,60 | PB39 | [Test]Dashboard(Farmer) | Huy | Done | 2 | 2 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
1,61 | PB40 | [Test]Lock/Unlock User Account | Huy | Done | 5 | 4 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
1,62 |  | Sprint 3 Review Meeting | All member | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
1,63 |  | Sprint 3 Retrospective | All member | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  |  |  | Total | 338 | 330 | 8 | 370 | 32 | 3 | 6 | 4 | 10 | 10 | 12 | 15 | 13 | 13 | 13 | 20 | 23 | 22 | 21 | 22 | 25 | 24 | 20 | 23 | 17 | 17
|  |  |  | Burn down | [5 empty] | 367 | 361 | 357 | 347 | 337 | 325 | 310 | 297 | 284 | 271 | 251 | 228 | 206 | 185 | 163 | 138 | 114 | 94 | 71 | 54 | 37
|  |  |  | Burn up | [5 empty] | 3 | 9 | 13 | 23 | 33 | 45 | 60 | 73 | 86 | 99 | 119 | 142 | 164 | 185 | 207 | 232 | 256 | 276 | 299 | 316 | 333
|  |  |  | Hour/Day | 16.0952
|  |  |  | Estimate |  |  |  |  | 370 | 347.9048 | 331.8095 | 315.7143 | 299.619 | 283.5238 | 267.4286 | 251.3333 | 235.2381 | 219.1429 | 203.0476 | 186.9524 | 170.8571 | 154.7619 | 138.6667 | 122.5714 | 106.4762 | 90.381 | 74.2857 | 58.1905 | 42.0952 | 26 | 0
|  |  |  | Actual |  |  |  |  | 370 | 367 | 361 | 357 | 347 | 337 | 325 | 310 | 297 | 284 | 271 | 251 | 228 | 206 | 185 | 163 | 138 | 114 | 94 | 71 | 54 | 37 | 0
[9 empty] | Trang | 0 | 0 | 0 | 3 | 4 | 4 | 6 | 7 | 7 | 7 | 6 | 8 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 65
[9 empty] | Huy | 0 | 2 | 2 | 3 | 2 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 7 | 7 | 9 | 5 | 2 | 61
[9 empty] | Thang | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 6 | 4 | 10 | 9 | 8 | 5 | 4 | 2 | 4 | 59
[9 empty] | Binh | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 4 | 8 | 5 | 8 | 9 | 8 | 5 | 5 | 1 | 62
[9 empty] | Bao | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 4 | 6 | 6 | 10 | 9 | 5 | 4 | 2 | 0 | 0 | 0 | 5 | 5 | 1 | 71
Note on B7: ====== ID#AAABuu-MR1o jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAABuu-MR1w jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On
1 | Login with Gmail account failed | Thang | 2025-09-15 |  |  | Huy | Resolved | Fixed Google OAuth configuration and updated authentication flow | 2025-09-16
2 | Firebase connection error | Binh | 2025-10-13 |  |  | Huy | Resolved | Updated API key | 2025-10-14
3 | Chatbot not responding | Bao | 2025-11-19 |  |  | Binh | Resolved | Fixed webhook flow with AI service | 2025-11-20
4 | User profile avatar not displayed | Huy | 2025-09-17 |  |  | Thang | Resolved | Fixed image URL mapping and updated user avatar loading API | 2025-09-18

## Retrospective
Retrospective Log
Sprint # | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks
1 | Team leader | Apply git for version management and jira for work division. | Continue daily standup meetings on time, with clear goals | Do not change the sprint scope suddenly | Sprint completed on schedule
2 | Developer | Write more automated test cases for the search module | Maintain thorough code reviews before merging | Avoid letting many small bugs accumulate | Some errors were discovered late
3 | Tester | Enhance coordination between testers and developers when testing functions | Continue to use effective task management tools | Do not hold unnecessary meetings | Testers need more testing resources

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms | Sprint Backlog Template (Excel)
Official Scrum Guide | https://scrumguides.org/scrum-guide.html | Product Backlog
Scrum Alliance | : https://www.scrumalliance.org/
Mountain Goat Software (Mike Cohn) | https://www.mountaingoatsoftware.com/agile/scrum/sprint-backlog