## Main
Scrum Project
Sprint Plan
| Sprint | Start | End | Status | Work planned (Committed) | Work spent (Delivered) | Remarks
| 1 | March 6,2026 | March 26,2026 | Complete | 487 | 494
| 2 | March 27,2026 | April 16,2026 | Complete | 485 | 511
| 3 | April 17,2026 | May 7,2026 | Complete | 345 | 346

## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Sign up | User | register a new account | I can access the system and use all features | User must input required fields: email,username, password, confirm password Email must be unique in the system Password must meet security policy Confirm password must match password System shows clear validation messages Account is created successfully |  | 1 |  |  |  | 1 | 20
PB02 | Log in | User | log in to my account | I can securely access my account | User enters email or username and password System verifies login information Valid → login successful and redirected Invalid → error message displayed Token generated |  | 1 |  |  |  | 1 | 20
PB03 | Log out | User | log out of my account | I can keep my account secure | User clicks logout Redirect to login page Cannot access system after logout |  | 2 |  |  |  | 1 | 5
PB04 | Forgot password | System,Admin | reset my password | I can regain access to my account | User enters registered email System sends reset email Link is time-limited User can set new password Password updated successfully |  | 2 |  |  |  | 1 | 10
PB05 | Home page interface(Admin) | Admin | see home page | I can learn about the functions | Page load time ≤ 3 seconds Only administrators are allowed access Displays a list of administrative modules: + System statistics dashboard + Supermarket management + Charity organization management + Delivery management + User management + System settings |  | 2 |  |  |  | 1 | 20
PB06 | Home page interface(Supermarket Admin) | Supermarket Admin | see home page | I can learn about the functions | Page load time ≤ 3 seconds Only users with Supermarket Admin privileges can access Displays functional modules as clear menus/cards, including: + Dashboard + Store Management + Employee Management + Policy Configuration + Coupon Management + Expiration Date Products + Donation Monitoring + Audit Log + Settings |  | 2 |  |  |  | 1 | 20
PB07 | Home page interface(Staff) | Staff | see home page | I can learn about the functions | Page load time ≤ 3 seconds Only users with Staff privileges can access Displays functional modules as clear menus/cards, including: + Dashboard + Category Management + Product Management + Inventory Batch + Expiration Date Tracking + Order Management + Donation Management + Settings |  | 2 |  |  |  | 1 | 20
PB08 | Home page interface(Charity) | Charity | see home page | I can learn about the functions | Page load time ≤ 3 seconds Only users with Charity permissions can access it Displays functional modules as clear menus/cards, including: + Dashboard + Donation Marketplace + History + Settings |  | 2 |  |  |  | 1 | 20
PB09 | Home page interface(Customer) | Customer | see home page | I can learn about the functions | Page load time ≤ 3 seconds Only logged-in users (Customers) can access Display functional modules as clear menus/tabs/cards, including: Homepage + Shop + Shopping Cart + Orders + Settings |  | 2 |  |  |  | 1 | 20
PB10 | Home page interface(Delivery) | Delivery | see home page | I can learn about the functions | Page load time ≤ 3 seconds Only users with Delivery permissions can access it Displays functional modules as clear menus/cards, including: + Dashboard (overview – placeholder) + Delivery Orders + Delivery History + Settings |  | 2 |  |  |  | 1 | 20
PB11 | View profile(Admin) | Admin | view my profile | I can verify and manage my account details | Display full name, email, phone number and role Data must match information stored in the database Sensitive information such as passwords should not be displayed Change password The page must load successfully without errors |  | 3 |  |  |  | 1 | 15
PB12 | View profile(Supermarket Admin) | Supermarket Admin | view my profile | I can verify and manage my account details | Display full name, email, phone number and role Data must match information stored in the database Sensitive information such as passwords should not be displayed Change password The page must load successfully without errors |  | 3 |  |  |  | 1 | 15
PB13 | View profile(Staff) | Staff | view my profile | I can verify and manage my account details | Display full name, email, phone number and role Data must match information stored in the database Sensitive information such as passwords should not be displayed Change password The page must load successfully without errors |  | 3 |  |  |  | 1 | 15
PB14 | View profile(Charity) | Charity | view my profile | I can verify and manage my account details | Display full name, email, phone number and role Data must match information stored in the database Sensitive information such as passwords should not be displayed Change password The page must load successfully without errors |  | 3 |  |  |  | 1 | 15
PB15 | View profile(Customer) | Customer | view my profile | I can verify and manage my account details | Display full name, email, phone number and role Data must match information stored in the database Sensitive information such as passwords should not be displayed Change password The page must load successfully without errors |  | 3 |  |  |  | 1 | 15
PB16 | View profile(Delivery) | Delivery | view my profile | I can verify and manage my account details | Display full name, email, phone number and role Data must match information stored in the database Sensitive information such as passwords should not be displayed Change password The page must load successfully without errors |  | 3 |  |  |  | 1 | 15
PB17 | Edit profile(Admin) | Admin | edit my profile information | I can keep my account information accurate and up to date | Users can update their name and phone number. Email address is editable. Input fields must be validated (required fields, formatting). Changes are successfully saved to the database. The system clearly displays success/error messages. Sensitive data (passwords) are not leaked. Only authenticated users can access this feature. |  | 3 |  |  |  | 1 | 10
PB18 | Edit profile(Supermarket Admin) | Supermarket Admin | edit my profile information | I can keep my account information accurate and up to date | Users can update their name and phone number. Email address is editable. Input fields must be validated (required fields, formatting). Changes are successfully saved to the database. The system clearly displays success/error messages. Sensitive data (passwords) are not leaked. Only authenticated users can access this feature. |  | 3 |  |  |  | 1 | 10
PB19 | Edit profile(Staff) | Staff | edit my profile information | I can keep my account information accurate and up to date | Users can update their name and phone number. Email address is editable. Input fields must be validated (required fields, formatting). Changes are successfully saved to the database. The system clearly displays success/error messages. Sensitive data (passwords) are not leaked. Only authenticated users can access this feature. |  | 3 |  |  |  | 1 | 10
PB20 | Edit profile(Charity) | Charity | edit my profile information | I can keep my account information accurate and up to date | Users can update their name and phone number. Email address is editable. Input fields must be validated (required fields, formatting). Changes are successfully saved to the database. The system clearly displays success/error messages. Sensitive data (passwords) are not leaked. Only authenticated users can access this feature. |  | 3 |  |  |  | 1 | 10
PB21 | Edit profile(Delivery) | Delivery | edit my profile information | I can keep my account information accurate and up to date | Users can update their name and phone number. Email address is editable. Input fields must be validated (required fields, formatting). Changes are successfully saved to the database. The system clearly displays success/error messages. Sensitive data (passwords) are not leaked. Only authenticated users can access this feature. |  | 3 |  |  |  | 1 | 10
PB22 | Edit profile(Customer) | Customer | edit my profile information | I can keep my account information accurate and up to date | Users can update their name and phone number. Email addresses are editable. Input fields must be validated (required fields, formatting). Changes are successfully saved to the database. The system clearly displays success/error messages. Sensitive data (passwords) are not leaked. Only authenticated users can access this feature. Addresses can be added/edited/deleted. |  | 3 |  |  |  | 1 | 10
PB23 | Lock/Unlock User Account | System,Admin | lock or unlock user accounts | I can restrict access for users who violate system policies | Admin can change user status (active/locked) Locked users cannot log in System displays account status clearly All actions must be logged for auditing |  | 2 |  |  |  | 1 | 20
PB24 | Supermarket manager | Admin | manage supermarket accounts | I can control system structure and entities | Create, update, delete supermarket accounts Assign a supermarket admin to each supermarket Validate required information before saving Prevent duplicate supermarket data |  | 1 |  |  |  | 2 | 25
PB25 | Charity organization management | Admin | manage charity organizations | I can control and support donation operations | Create, update, delete charity organizations Activate or deactivate organization status Validate unique email for each organization Display list of organizations |  | 1 |  |  |  | 2 | 25
PB26 | Delivery management | Admin | manage delivery accounts | I can handle logistics and order delivery | Create, update, delete delivery staff Track delivery status Ensure data consistency |  | 1 |  |  |  | 2 | 25
PB27 | User management | Admin | manage all user accounts in the system | I can control access | System validates required fields before saving Admin can search and filter users All changes must be saved in the database |  | 1 |  |  |  | 2 | 25
PB28 | Store management | Supermarket Admin | manage stores under my supermarket | I can organize and control store operations | Create, update, delete store Validate required information Display store list |  | 1 |  |  |  | 2 | 25
PB29 | Store staff management | Supermarket Admin | personnel management | I can assign responsibilities and manage operations | Create and assign staff to store Update staff information Lock/unlock staff account Staff must belong to a specific store |  | 1 |  |  |  | 2 | 25
PB30 | Policy configuration | Supermarket Admin | configure expiry and discount policies | the system can automatically handle near-expiry products | Set near-expiry threshold Configure discount percentage rules Save configuration successfully Apply policy to products |  | 1 |  |  |  | 2 | 20
PB31 | Monitoring donations | Supermarket Admin | monitor donation activities | I can evaluate donation impact | Display total donation quantity Show donation history Filter by date/time Data must be accurate |  | 1 |  |  |  | 2 | 20
PB32 | Coupon Management | Supermarket Admin | manage coupon codes (create, update, delete) | I can run promotional campaigns effectively | Create coupon with code, discount value (percentage or fixed), expiry date Update coupon information Disable or delete coupon Coupon code must be unique Expired coupons cannot be used Display coupon list Support filtering/searching by status (active, expired, disabled) Data must be stored correctly in the system |  | 1 |  |  |  | 2 | 25
PB33 | Expiration Date Tracking | Supermarket Admin | monitor and track product expiration dates across stores | I can ensure product quality and prevent expired products from being sold | System automatically compares expiry date with current date Expired products are marked as “expired” Near-expiry products can be identified based on configured threshold Expired products are not displayed to customers Supermarket admin can view expiration data across all stores Support filtering by store, product, expiry status, date Data must be restricted to the admin’s supermarket System prevents selling expired products
PB34 | Category management | Staff | manage product categories | products are organized clearly | Add, edit, delete categories Validate category name Save data to database |  | 1 |  |  |  | 2 | 25
PB35 | Product management | Staff | manage products and pricing | product data is accurate | Add, update, delete product Validate name, price, stock Prevent negative values Changes reflect immediately |  | 1 |  |  |  | 2 | 25
PB36 | Inventory | Staff | manage inventory by batch | I can track expiry dates precisely | Add inventory batch (batch code, expiry date, quantity) Expiry date must be valid Update stock per batch Display batch list |  | 1 |  |  |  | 2 | 15
PB37 | Expiration Date Tracking | Staff | automatically check product expiry | expired products are not sold | Compare expiry date with current date Mark expired products Hide expired products from marketplace |  | 2 |  |  |  | 2 | 15
PB38 | Order management | Staff | manage customer orders | I can process and fulfill them | View order list Update status Cancel if needed |  | 1 |  |  |  | 2 | 25
PB39 | Donation management | Staff | manage donation process | distribute products | Create donation Approve requests Track status |  | 1 |  |  |  | 2 | 25
PB40 | Donation Offer Marketplace | Charity | browse and view available donation offers from supermarkets | I can request suitable products for my organization | Display list of available donation offers (products near expiry or unsold stock) Each offer includes: product name, quantity, expiry date, supermarket/store info Only show offers that are still available (not expired or fully claimed) Charity can submit a request to receive donation System validates request (cannot exceed available quantity) Request is recorded with status = “pending” Page loads efficiently (<3 seconds) |  | 2 |  |  |  | 2 | 20
PB41 | Donation History & Status | Charity | view my donation request history and status | I can track which donations are approved, pending, or rejected | Display list of all donation requests made by the charity Each record includes: product name, quantity requested, request date, status Status includes: pending, approved, rejected, completed Allow filtering by status and date Data must belong to the logged-in charity account Page supports pagination for large data |  | 2 |  |  |  | 2 | 20
PB42 | Orders(Delivery) | Delivery | view and manage assigned delivery orders | I can complete deliveries accurately and on time | Display list of orders assigned to the delivery staff Each order shows: order ID, customer info, delivery address, status Delivery staff can update order status (assigned → delivering → delivered) System validates status transitions (cannot skip steps) Updated status must be saved to database immediately Delivery staff can view order details |  | 2 |  |  |  | 2 | 25
PB43 | Delivery History | Delivery | view my delivery history | I can track completed deliveries and performance | Display list of completed delivery orders Each record shows: order ID, delivery date, status Allow filtering by date range Data must be accurate and belong to the logged-in delivery staff Page loads without errors |  | 2 |  |  |  | 2 | 25
PB44 | Online marketplace | Customer | browse a list of available near-expiry products | I can choose products to purchase at discounted prices | Display product list with: name, price, discount, expiry date, stock Only show products that are not expired Allow sorting (price, expiry date, discount) Allow filtering by category Page loads within acceptable time (<3 seconds) Clicking a product navigates to product detail page |  | 2 |  |  |  | 2 | 25
PB45 | Search & Filter Products | Customer | search and filter products by name and category | I can quickly find relevant products | User can search products by keyword (name) User can filter by category Results must match search criteria Results update dynamically or after search action No expired products are displayed System performance acceptable |  | 2 |  |  |  | 2 | 20
PB46 | Shopping cart | Customer | add, remove or update products in the cart | I can manage items before checkout | User can add products to cart User can update quantity of each product User can remove products from cart Total price is calculated correctly Cannot add quantity greater than available stock Cart persists during session |  | 2 |  |  |  | 3 | 25
PB47 | Orders(Customer) | Customer | view my orders | I can track my purchases and order status | Display list of customer orders Each order shows: order ID, total price, status, payment method User can view order details Orders are sorted by latest first Data must be accurate |  | 2 |  |  |  | 3 | 25 | 25 | 25 | 25
PB48 | Coupon Management | Supermarket Admin | create, edit, delete, and manage coupon codes | I can run promotional campaigns | Create coupon with code, discount value, expiry date Update or disable coupon Validate coupon uniqueness Expired coupons cannot be used Display coupon list |  | 1 |  |  |  | 3 | 25
PB49 | Apply coupon code at checkout | Customer | apply a coupon code during checkout | I can receive a discount | User can enter coupon code System validates code Discount applied correctly Invalid code shows error message Cannot apply multiple unsupported coupons |  | 2 |  |  |  | 3 | 20
PB50 | Checkout | Customer | review order and confirm payment | I can complete the purchase | Display order summary (items, price, discount, total) Allow selecting address and payment method Confirm order successfully Save order to database Show confirmation message |  | 1 |  |  |  | 3 | 25
PB51 | COD payment | Customer | choose cash on delivery | pay after receiving the goods successfully | COD option is displayed in payment methods User can select COD before placing order Order is saved with payment method = COD System shows instruction for COD payment Order status updates to “completed” after successful delivery No online payment is required |  | 3 |  |  |  | 3 | 10
PB52 | VNPAY Payment | Customer | payment by MoMo wallet | complete transactions quickly | User can select MoMo payment method System redirects to MoMo payment gateway Payment success updates order status to “paid” Payment failure keeps order in “pending” state Transaction information is stored in database System shows clear success/failure message |  | 3 |  |  |  | 3 | 20
PB53 | Order history | Customer | view my previous orders | I can track previous purchases | Display list of all past orders Each order includes: order ID, date, total, status Allow user to view order details Support pagination for large data Data must belong to logged-in user |  | 3 |  |  |  | 3 | 25
PB54 | Dashboard(Admin) | Admin | view system statistics | I can monitor overall system performance | Display total users Data updates correctly Only admin access |  | 2 |  |  |  | 3 | 20
PB55 | Dashboard(Supermarket Admin) | Supermarket Admin | view a dashboard with business metrics | I can track performance across stores | Display total number of stores, staff, and products Show number of near-expiry products Show total orders and revenue Display donation vs sales statistics Allow filtering by time (daily, monthly) Data must reflect only the admin’s supermarket Dashboard loads quickly and charts render correctly |  | 3 |  |  |  | 3 | 15
PB56 | Dashboard(Staff) | Staff | view my store dashboard | I can manage daily operations efficiently | Display total inventory and near-expiry products Show pending and completed orders Show alerts for low stock and near-expiry items Data must belong to assigned store Page loads correctly without errors |  | 3 |  |  |  | 3 | 10
PB57 | Dashboard(Charity) | Charity | view donation dashboard | I can track received and pending donations | Display list of received donations Show pending donation requests Show donation statistics Data must belong to the organization Page loads correctly |  | 3 |  |  |  | 3 | 10
PB58 | Dashboard(Customer) | Customer | view my personal dashboard | I can manage my shopping activities | Display recent orders Show total spending Show active coupons (if any) Page loads successfully |  | 3 |  |  |  | 3 | 10
PB59 | Dashboard(Delivery) | Delivery | view my personal dashboard | I can track my assigned and completed deliveries | Display assigned orders Show completed deliveries Show delivery performance metrics Page loads correctly |  | 3 |  |  |  | 3 | 10
PB60 | Audit log(Supermarket Admin) | Supermarket Admin | view audit logs related to my supermarket | I can monitor activities and ensure compliance within my organization | Display logs of actions performed within the supermarket scope (staff actions, product updates, orders, donations) Each log must include: user ID, action type, timestamp, affected entity Allow filtering logs by date range, user, and action type Logs must be read-only (cannot be edited or deleted) Only logs related to the admin’s supermarket are visible (data isolation) Page must load efficiently (<3 seconds) | 3 | 3 | 15 |  |  | 3 | 15
PB61 | Reports and analysis | Supermarket Admin | view reports and analyze business data | I can make informed decisions and improve business performance | Reports include: revenue, orders, products, donations Compare data between periods and show % increase/decrease Identify top-performing stores/products Allow filtering by store, category, and time Data must be accurate and restricted to the admin’s supermarket | 3 | 3 | 15 |  |  | 3 | 15
Note on M7: ====== ID#AAABuu-MR1k (2025-12-07 14:55:26) Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.
Note on N7: ====== ID#AAABuu-MR10 jan samuelsson (2025-12-07 14:55:26) Just rough numbers, 5,10,15,20 etc. Not 7, 13, 21 etc.

## Sprint 1 Backlog
Sprint 1 Backlog
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
1,1 |  | Sprint Detail Plan | Binh | Done | 4 | 3 | 1 | 3 | -1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,2 |  | Planning meeting | All member | Done | 4 | 4 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,3 |  | Create Proposal Document | Thang | Done | 6 | 6 | 0 | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,4 |  | Create Project Plan Document | Trang | Done | 5 | 3 | 2 | 5 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,5 |  | Create Product Backlog Document | Thang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,6 |  | Create User Story Document | Bao | Done | 5 | 4 | 1 | 5 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,7 |  | Create Database Design Document | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,8 |  | Create Interface Design Document | Bao | Done | 5 | 4 | 1 | 4 | -1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,9 |  | Create Architecture Design Document | Binh | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,10 |  | Create Sprint 1 Backlog | Huy | Done | 5 | 5 | 0 | 6 | 1 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,11 |  | Create Test Plan for Sprint 1 | Huy | Done | 2 | 3 | -1 | 3 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,12 |  | Create Test Case for Sprint 1 | Trang | Done | 3 | 3 | 0 | 5 | 2 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,13 |  | Create Database | Bao | Done | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 3 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,14 | PB01 | [Design]Sign up | Trang | Done | 5 | 5 | 0 | 7 | 2 | 0 | 0 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,15 | PB02 | [Design]Log in | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,16 | PB03 | [Design]Home page interface(Admin) | Huy | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,17 | PB04 | [Design]Home page interface(Supermarket Admin) | Huy | Done | 5 | 5 | 0 | 7 | 2 | 0 | 0 | 0 | 2 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,18 | PB05 | [Design]Home page interface(Staff) | Thang | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,19 | PB06 | [Design]Home page interface(Charity) | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,20 | PB07 | [Design]Home page interface(Delivery) | Bao | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,21 | PB08 | [Design]Home page interface(Customer) | Binh | Done | 5 | 5 | 0 | 7 | 2 | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,22 | PB09 | [Design]Log out | All | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,23 | PB10 | [Design]Forgot password | Huy | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,24 | PB11 | [Design]View profile(Admin) | Huy | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,25 | PB12 | [Design]View profile(Supermarket Admin) | Huy | Done | 5 | 4 | 1 | 6 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,26 | PB13 | [Design]View profile(Staff) | Thang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,27 | PB14 | [Design]View profile(Charity) | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,28 | PB15 | [Design]View profile(Delivery) | Bao | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,29 | PB16 | [Design]View profile(Customer) | Binh | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,30 | PB23 | [Design]Lock/Unlock User Account | Huy | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,31 | PB01 | [FE]Sign up | Trang | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,32 | PB01 | [BE]Sign up | Trang | Done | 7 | 6 | 1 | 6 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,33 | PB02 | [FE]Log in | Trang | Done | 8 | 10 | -2 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,34 | PB02 | [BE]Log in | Trang | Done | 6 | 5 | 1 | 5 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,35 | PB03 | [FE]Home page interface(Admin) | Binh | Done | 8 | 8 | 0 | 7 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,36 | PB03 | [BE]Home page interface(Admin) | Binh | Done | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,37 | PB04 | [FE]Home page interface(Supermarket Admin) | Huy | Done | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,38 | PB04 | [BE]Home page interface(Supermarket Admin) | Huy | Done | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,39 | PB05 | [FE]Home page interface(Staff) | Thang | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,40 | PB05 | [BE]Home page interface(Staff) | Thang | Done | 7 | 6 | 1 | 6 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,41 | PB06 | [FE]Home page interface(Charity) | Trang | Done | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,42 | PB06 | [BE]Home page interface(Charity) | Trang | Done | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,43 | PB07 | [FE]Home page interface(Delivery) | Bao | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,44 | PB07 | [BE]Home page interface(Delivery) | Bao | Done | 7 | 7 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,45 | PB08 | [FE]Home page interface(Customer) | Binh | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,46 | PB08 | [BE]Home page interface(Customer) | Binh | Done | 7 | 5 | 2 | 5 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,47 | PB09 | [FE]Log out | All | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,48 | PB09 | [BE]Log out | All | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,49 | PB10 | [FE]Forgot password | Huy | Done | 4 | 4 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,50 | PB10 | [BE]Forgot password | Huy | Done | 7 | 7 | 0 | 6 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,51 | PB11 | [FE]View profile(Admin) | Bao | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,52 | PB11 | [BE]View profile(Admin) | Bao | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,53 | PB12 | [FE]View profile(Supermarket Admin) | Thang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,54 | PB12 | [BE]View profile(Supermarket Admin) | Thang | Done | 6 | 6 | 0 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0
1,55 | PB13 | [FE]View profile(Staff) | Thang | Done | 8 | 6 | 2 | 6 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
1,56 | PB13 | [BE]View profile(Staff) | Thang | Done | 7 | 6 | 1 | 6 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
1,57 | PB14 | [FE]]View profile(Charity) | Trang | Done | 8 | 6 | 2 | 6 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
1,58 | PB14 | [BE]]View profile(Charity) | Trang | Done | 7 | 7 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0
1,59 | PB15 | [FE]View profile(Delivery) | Bao | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
1,60 | PB15 | [BE]View profile(Delivery) | Bao | Done | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0
1,61 | PB16 | [FE]View profile(Customer) | Binh | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
1,62 | PB16 | [BE]View profile(Customer) | Binh | Done | 6 | 6 | 0 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0
1,63 | PB17 | [BE]Edit profile(Admin) | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
1,64 | PB18 | [BE]Edit profile(Supermarket Admin) | Binh | Done | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0
1,65 | PB19 | [BE]Edit profile(Staff) | Thang | Done | 6 | 4 | 2 | 4 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0
1,66 | PB20 | [BE]Edit profile(Charity) | Thang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0
1,67 | PB21 | [BE]Edit profile(Delivery) | Bao | Done | 8 | 6 | 2 | 6 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0
1,68 | PB22 | [BE]Edit profile(Customer) | Binh | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0
1,69 | PB23 | [FE]Lock/Unlock User Account | Huy | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0
1,70 | PB23 | [BE]Lock/Unlock User Account | Thang | Done | 8 | 8 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 2 | 2 | 0 | 0 | 0
1,71 | PB01 | [Test]Sign up | Trang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
1,72 | PB02 | [Test]Log in | Trang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1,73 | PB03 | [Test]Home page interface(Admin) | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
1,74 | PB04 | [Test]Home page interface(Supermarket Admin) | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,75 | PB05 | [Test]Home page interface(Staff) | Thang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1,76 | PB06 | [Test]Home page interface(Charity) | Trang | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
1,77 | PB07 | [Test]Home page interface(Delivery) | Bao | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0
1,78 | PB08 | [Test]Home page interface(Customer) | Binh | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
1,79 | PB09 | [Test]Log out | All | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,80 | PB10 | [Test]Forgot password | Huy | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
1,81 | PB11 | [Test]View profile(Admin) | Huy | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
1,82 | PB12 | [Test]View profile(Supermarket Admin) | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,83 | PB13 | [Test]View profile(Staff) | Thang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0
1,84 | PB14 | [Test]View profile(Charity) | Trang | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
1,85 | PB15 | [Test]View profile(Delivery) | Bao | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
1,86 | PB16 | [Test]View profile(Customer) | Binh | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,87 | PB17 | [Test]Edit profile(Admin) | Huy | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
1,88 | PB18 | [Test]Edit profile(Supermarket Admin) | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,89 | PB19 | [Test]Edit profile(Staff) | Thang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
1,90 | PB20 | [Test]Edit profile(Charity) | Trang | Done | 3 | 3 | 0 | 2 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
1,91 | PB21 | [Test]Edit profile(Delivery) | Bao | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
1,92 | PB22 | [Test]Edit profile(Customer) | Binh | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,93 | PB23 | [Test]Lock/Unlock User Account | Binh | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
1,94 |  | Sprint 1 Review Meeting | All member | Done | 3 | 3 | 0 | 2 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
1,95 |  | Sprint 1 Retrospective | All member | Done | 3 | 3 | 0 | 2 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | Total | 494 | 466 | 28 | 487 | -7 | 12 | 19 | 25 | 24 | 24 | 24 | 22 | 24 | 25 | 24 | 24 | 26 | 27 | 25 | 24 | 28 | 23 | 18 | 29 | 36 | 4
|  |  |  | Burn down | [5 empty] | 482 | 463 | 438 | 414 | 390 | 366 | 344 | 320 | 295 | 271 | 247 | 221 | 194 | 169 | 145 | 117 | 94 | 76 | 47 | 11 | 7
|  |  |  | Burn up | [5 empty] | 12 | 31 | 56 | 80 | 104 | 128 | 150 | 174 | 199 | 223 | 247 | 273 | 300 | 325 | 349 | 377 | 400 | 418 | 447 | 483 | 487
|  |  |  | Hour/Day | 22.1905
|  |  |  | Estimate |  |  |  |  | 494 | 471.8095 | 449.619 | 427.4286 | 405.2381 | 383.0476 | 360.8571 | 338.6667 | 316.4762 | 294.2857 | 272.0952 | 249.9048 | 227.7143 | 205.5238 | 183.3333 | 161.1429 | 138.9524 | 116.7619 | 94.5714 | 72.381 | 50.1905 | 28 | 0
|  |  |  | Actual |  |  |  |  | 494 | 482 | 463 | 438 | 414 | 390 | 366 | 344 | 320 | 295 | 271 | 247 | 221 | 194 | 169 | 145 | 117 | 94 | 76 | 47 | 11 | 7 | 0
[9 empty] | Trang | 3 | 3 | 7 | 8 | 5 | 2 | 8 | 6 | 10 | 10 | 8 | 4 | 0 | 6 | 6 | 2 | 0 | 2 | 8 | 5 | 0 | 103
[9 empty] | Huy | 0 | 4 | 9 | 9 | 7 | 6 | 4 | 3 | 5 | 6 | 7 | 3 | 5 | 0 | 0 | 3 | 6 | 4 | 10 | 9 | 0 | 100
[9 empty] | Thang | 2 | 3 | 4 | 2 | 4 | 4 | 1 | 6 | 6 | 2 | 1 | 1 | 3 | 8 | 9 | 10 | 9 | 4 | 3 | 7 | 0 | 89
[9 empty] | Binh | 2 | 1 | 5 | 2 | 1 | 3 | 5 | 5 | 4 | 6 | 3 | 6 | 5 | 3 | 4 | 8 | 6 | 5 | 4 | 7 | 0 | 85
[9 empty] | Bao | 3 | 6 | 0 | 3 | 5 | 7 | 2 | 4 | 0 | 0 | 5 | 10 | 9 | 6 | 5 | 5 | 2 | 3 | 2 | 6 | 0 | 83
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart

## Sprint 2 Backlog
Sprint 2 Backlog
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
1,1 |  | Sprint Detail Plan | All member | Done | 4 | 3 | 1 | 3 | -1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,2 |  | Planning Meeting | All member | Done | 4 | 4 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,3 |  | Update Database Design Document | Bao | Done | 4 | 4 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,4 |  | Update Interface Design Document | Bao | Done | 5 | 4 | 1 | 4 | -1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,5 |  | Create Sprint 2 Backlog | Huy | Done | 5 | 5 | 0 | 6 | 1 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,6 |  | Create Test Plan for Sprint 2 | Thang | Done | 3 | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,7 |  | Create Test Case for Sprint 2 | Binh | Done | 3 | 3 | 0 | 5 | 2 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,8 |  | Update Database | Bao | Done | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 3 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,9 | PB24 | [Design]Supermarket manager | Huy | Done | 5 | 5 | 0 | 5 | 0 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,10 | PB25 | [Design]Charity organization management | Huy | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,11 | PB26 | [Design]Delivery management | Huy | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,12 | PB27 | [Design]User management | Huy | Done | 5 | 4 | 1 | 7 | 2 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,13 | PB28 | [Design]Store management | Bao | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,14 | PB29 | [Design]Store staff management | Bao | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,15 | PB30 | [Design]Policy configuration | Trang | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,16 | PB31 | [Design]Monitoring donations | Trang | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,17 | PB32 | [Design]Coupon Management | Binh | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,18 | PB33 | [Design]Expiration date tracking(Supermarket admin) | Binh | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,19 | PB34 | [Design]Category Management | Thang | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,20 | PB35 | [Design]Product Management | Thang | Done | 5 | 4 | 1 | 5 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,21 | PB36 | [Design]Inventory | Thang | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,22 | PB37 | [Design]Expiration date tracking(Staff) | Thang | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,23 | PB38 | [Design]Order management | Thang | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,24 | PB39 | [Design]Donation management | Thang | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,25 | PB40 | [Design]Donation Offer Marketplace | Trang | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,26 | PB41 | [Design]Donation History & Status | Trang | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,27 | PB42 | [Design]Orders(Delivery) | Bao | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,28 | PB43 | [Design]Delivery History | Bao | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,29 | PB44 | [Design]Online marketplace | Binh | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,30 | PB45 | [Design]Search & Filter Products | Binh | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,31 | PB24 | [FE]Supermarket manager | Huy | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,32 | PB24 | [BE]Supermarket manager | Huy | Done | 7 | 6 | 1 | 6 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,33 | PB25 | [FE]Charity organization management | Binh | Done | 8 | 10 | -2 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,34 | PB25 | [BE]Charity organization management | Binh | Done | 6 | 5 | 1 | 5 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,35 | PB26 | [FE]Delivery management | Huy | Done | 8 | 8 | 0 | 7 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,36 | PB26 | [BE]Delivery management | Huy | Done | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,37 | PB27 | [FE]User management | Huy | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,38 | PB27 | [BE]User management | Huy | Done | 6 | 6 | 0 | 4 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,39 | PB28 | [FE]Store management | Trang | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,40 | PB28 | [BE]Store management | Trang | Done | 7 | 6 | 1 | 6 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,41 | PB29 | [FE]Store staff management | Huy | Done | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,42 | PB29 | [BE]Store staff management | Huy | Done | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,43 | PB30 | [FE]Policy configuration | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,44 | PB30 | [BE]Policy configuration | Trang | Done | 7 | 7 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,45 | PB31 | [FE]Monitoring donations | Trang | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,46 | PB31 | [BE]Monitoring donations | Thang | Done | 7 | 5 | 2 | 5 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,47 | PB32 | [FE]Coupon Management | Bao | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,48 | PB32 | [BE]Coupon Management | Bao | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,49 | PB33 | [FE]Expiration date tracking(Supermarket admin) | Binh | Done | 4 | 4 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,50 | PB33 | [BE]Expiration date tracking(Supermarket admin) | Binh | Done | 7 | 7 | 0 | 6 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,51 | PB34 | [FE]Category Management | Thang | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,52 | PB34 | [BE]Category Management | Thang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,53 | PB35 | [FE]Product Management | Thang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,54 | PB35 | [BE]Product Management | Bao | Done | 6 | 6 | 0 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0
1,55 | PB36 | [FE]Inventory | Bao | Done | 8 | 6 | 2 | 6 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
1,56 | PB36 | [BE]Inventory | Thang | Done | 7 | 6 | 1 | 6 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
1,57 | PB37 | [FE]Expiration date tracking(Staff) | Thang | Done | 8 | 6 | 2 | 6 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
1,58 | PB37 | [BE]Expiration date tracking(Staff) | Binh | Done | 7 | 7 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0
1,59 | PB38 | [FE]Order management | Binh | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
1,60 | PB38 | [BE]Order management | Bao | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1,61 | PB39 | [FE]Donation management | Bao | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
1,62 | PB39 | [BE]Donation management | Thang | Done | 6 | 6 | 0 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0
1,63 | PB40 | [FE]Donation Offer Marketplace | Trang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
1,64 | PB40 | [BE]Donation Offer Marketplace | Trang | Done | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0
1,65 | PB41 | [FE]Donation History & Status | Trang | Done | 6 | 4 | 2 | 4 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0
1,66 | PB41 | [BE]Donation History & Status | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0
1,67 | PB42 | [FE]Orders(Delivery) | Thang | Done | 8 | 6 | 2 | 6 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 0 | 0
1,68 | PB42 | [BE]Orders(Delivery) | Bao | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0
1,69 | PB43 | [FE]Delivery History | Bao | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0
1,70 | PB43 | [BE]Delivery History | Bao | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0
1,71 | PB44 | [FE]Online marketplace | Binh | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0
1,72 | PB44 | [BE]Online marketplace | Binh | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0
1,73 | PB45 | [FE]Search & Filter Products | Binh | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
1,74 | PB45 | [BE]Search & Filter Products | Binh | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
1,75 | PB24 | [Test]Supermarket manager | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
1,76 | PB25 | [Test]Charity organization management | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1,77 | PB26 | [Test]Delivery management | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
1,78 | PB27 | [Test]User management | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,79 | PB28 | [Test]Store management | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0
1,80 | PB29 | [Test]Policy configuration | Huy | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
1,81 | PB30 | [Test]Monitoring donations | Huy | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0
1,82 | PB31 | [Test]Monitoring donations | Huy | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
1,83 | PB32 | [Test]Coupon Management | Trang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,84 | PB33 | [Test]Expiration date tracking(Supermarket admin) | Trang | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
1,85 | PB34 | [Test]Category Management | Thang | Done | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
1,86 | PB35 | [Test]Product Management | Thang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,87 | PB36 | [Test]Inventory | Thang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0
1,88 | PB37 | [Test]Expiration date tracking(Staff) | Thang | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
1,89 | PB38 | [Test]Order management | Thang | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
1,90 | PB39 | [Test]Donation management | Thang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,91 | PB40 | [Test]Donation Offer Marketplace | Trang | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
1,92 | PB41 | [Test]Donation History & Status | Trang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,93 | PB42 | [Test]Orders(Delivery) | Bao | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
1,94 | PB43 | [Test]Delivery History | Bao | Done | 3 | 3 | 0 | 2 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
1,95 | PB44 | [Test]Online marketplace | Binh | Done | 4 | 3 | 1 | 3 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
1,96 | PB45 | [Test]Search & Filter Products | Binh | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,97 |  | Sprint 2 Review Meeting | All member | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
1,98 |  | Sprint 2 Retrospective | All member | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  |  |  | Total | 511 | 478 | 33 | 485 | -26 | 6 | 19 | 15 | 20 | 20 | 25 | 32 | 31 | 19 | 17 | 25 | 27 | 27 | 23 | 22 | 30 | 33 | 27 | 28 | 30 | 8
|  |  |  | Burn down | [5 empty] | 479 | 460 | 445 | 425 | 405 | 380 | 348 | 317 | 298 | 281 | 256 | 229 | 202 | 179 | 157 | 127 | 94 | 67 | 39 | 9 | 1
|  |  |  | Burn up | [5 empty] | 6 | 25 | 40 | 60 | 80 | 105 | 137 | 168 | 187 | 204 | 229 | 256 | 283 | 306 | 328 | 358 | 391 | 418 | 446 | 476 | 484
|  |  |  | Hour/Day | 22.7619
|  |  |  | Estimate |  |  |  |  | 511 | 488.2381 | 465.4762 | 442.7143 | 419.9524 | 397.1905 | 374.4286 | 351.6667 | 328.9048 | 306.1429 | 283.381 | 260.619 | 237.8571 | 215.0952 | 192.3333 | 169.5714 | 146.8095 | 124.0476 | 101.2857 | 78.5238 | 55.7619 | 33 | 0
|  |  |  | Actual |  |  |  |  | 511 | 505 | 486 | 471 | 451 | 431 | 406 | 374 | 343 | 324 | 307 | 282 | 255 | 228 | 205 | 183 | 153 | 120 | 93 | 65 | 35 | 27 | 0
[9 empty] | Trang | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 10 | 7 | 2 | 5 | 8 | 8 | 0 | 0 | 9 | 10 | 0 | 6 | 7 | 1 | 88
[9 empty] | Huy | 0 | 4 | 10 | 8 | 4 | 5 | 7 | 8 | 10 | 10 | 8 | 3 | 0 | 0 | 0 | 0 | 6 | 10 | 10 | 2 | 1 | 106
[9 empty] | Thang | 0 | 3 | 0 | 4 | 5 | 8 | 8 | 2 | 0 | 0 | 3 | 9 | 9 | 9 | 8 | 8 | 0 | 2 | 10 | 10 | 1 | 99
[9 empty] | Binh | 0 | 3 | 2 | 5 | 4 | 0 | 3 | 8 | 2 | 5 | 9 | 5 | 5 | 5 | 5 | 3 | 8 | 10 | 2 | 5 | 1 | 90
[9 empty] | Bao | 2 | 6 | 3 | 3 | 7 | 7 | 4 | 3 | 0 | 0 | 0 | 2 | 5 | 9 | 9 | 10 | 9 | 5 | 0 | 6 | 1 | 91
Note on B7: ====== ID#AAABuu-MR14 jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAABuu-MR1s jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 2 Reports
Reports & Dashboards
Burn down Chart

## Sprint 3 Backlog
Sprint 3 Backlog
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
1,1 |  | Sprint Detail Plan | All member | Done | 6 | 4 | 2 | 4 | -2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,2 |  | Planning Meeting | Huy | Done | 4 | 4 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,3 |  | Update Database Design Document | Bao | Done | 4 | 4 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,4 |  | Update Interface Design Document | Bao | Done | 5 | 4 | 1 | 4 | -1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,5 |  | Create Sprint 3 Backlog | Huy | Done | 5 | 5 | 0 | 6 | 1 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,6 |  | Create Test Plan for Sprint 3 | Thang | Done | 4 | 4 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,7 |  | Create Test Case for Sprint 3 | Binh | Done | 4 | 4 | 0 | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,8 | PB46 | [Design]Shopping cart | Binh | Done | 5 | 5 | 0 | 5 | 0 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,9 | PB47 | [Design]Orders(Customer) | Binh | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,10 | PB48 | [Design]Coupon Management | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,11 | PB49 | [Design]Apply coupon code at checkout | Huy | Done | 5 | 4 | 1 | 7 | 2 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,12 | PB50 | [Design]Checkout | Huy | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,13 | PB52 | [Design]MoMo Payment | Binh | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,14 | PB53 | [Design]Order history | Binh | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,15 | PB54 | [Design]Dashboard(Admin) | Huy | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,16 | PB55 | [Design]Dashboard(Supermarket Admin) | Trang | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,17 | PB56 | [Design]Dashboard(Staff) | Thang | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,18 | PB57 | [Design]Dashboard(Charity) | Trang | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,19 | PB58 | [Design]Dashboard(Customer) | Bao | Done | 5 | 4 | 1 | 5 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,20 | PB59 | [Design]Dashboard(Delivery) | Bao | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,21 | PB60 | [Design]Audit log | Trang | Done | 5 | 5 | 0 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,22 | PB61 | [Design]Reports and analysis | Trang | Done | 5 | 5 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,23 | PB46 | [FE]Shopping cart | Binh | Done | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,24 | PB46 | [BE]Shopping cart | Binh | Done | 7 | 6 | 1 | 6 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,25 | PB47 | [FE]Orders(Customer) | Thang | Done | 8 | 10 | -2 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,26 | PB47 | [BE]Orders(Customer) | Thang | Done | 6 | 5 | 1 | 5 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,27 | PB48 | [FE]Coupon Management | Trang | Done | 8 | 8 | 0 | 7 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,28 | PB48 | [BE]Coupon Management | Trang | Done | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,29 | PB49 | [FE]Apply coupon code at checkout | Binh | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,30 | PB49 | [BE]Apply coupon code at checkout | Bao | Done | 6 | 6 | 0 | 4 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,31 | PB50 | [FE]Checkout | Thang | Done | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,32 | PB50 | [BE]Checkout | Bao | Done | 7 | 6 | 1 | 6 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,33 | PB51 | [BE]COD payment | Bao | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,34 | PB52 | [FE]VNPAY Payment | Binh | Done | 5 | 7 | -2 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,35 | PB52 | [BE]VNPAY Payment | Binh | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,36 | PB53 | [FE]Order history | Thang | Done | 7 | 7 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,37 | PB53 | [BE]Order history | Thang | Done | 6 | 8 | -2 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,38 | PB54 | [FE]Dashboard(Admin) | Huy | Done | 7 | 5 | 2 | 5 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,39 | PB54 | [BE]Dashboard(Admin) | Huy | Done | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,40 | PB55 | [FE]Dashboard(Supermarket Admin) | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,41 | PB55 | [BE]Dashboard(Supermarket Admin) | Trang | Done | 4 | 4 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1,42 | PB56 | [FE]Dashboard(Staff) | Thang | Done | 6 | 8 | -2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1,43 | PB56 | [BE]Dashboard(Staff) | Bao | Done | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1,44 | PB57 | [FE]Dashboard(Charity) | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0
1,45 | PB57 | [BE]Dashboard(Charity) | Trang | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0
1,46 | PB58 | [FE]Dashboard(Customer) | Binh | Done | 5 | 6 | -1 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 0 | 0 | 0 | 0
1,47 | PB58 | [BE]Dashboard(Customer) | Binh | Done | 5 | 7 | -2 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 0
1,48 | PB59 | [FE]Dashboard(Delivery) | Bao | Done | 7 | 6 | 1 | 6 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0
1,49 | PB59 | [BE]Dashboard(Delivery) | Bao | Done | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
1,50 | PB60 | [FE]Audit log | Huy | Done | 8 | 6 | 2 | 6 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0
1,51 | PB60 | [BE]Audit log | Huy | Done | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0
1,52 | PB61 | [FE]Reports and analysis | Huy | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
1,53 | PB61 | [BE]Reports and analysis | Huy | Done | 5 | 4 | 1 | 4 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
1,54 | PB46 | [Test]Shopping cart | Bao | Done | 3 | 4 | -1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0
1,55 | PB47 | [Test]Orders(Customer) | Bao | Done | 3 | 4 | -1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1,56 | PB48 | [Test]Coupon Management | Trang | Done | 3 | 4 | -1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1,57 | PB49 | [Test]Apply coupon code at checkout | Binh | Done | 3 | 4 | -1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,58 | PB50 | [Test]Checkout | Binh | Done | 3 | 4 | -1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
1,59 | PB51 | [Test]COD payment | Binh | Done | 3 | 2 | 1 | 2 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
1,60 | PB52 | [Test]MoMo Payment | Thang | Done | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0
1,61 | PB53 | [Test]Order history | Thang | Done | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
1,62 | PB54 | [Test]Dashboard(Admin) | Huy | Done | 3 | 4 | -1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,63 | PB55 | [Test]Dashboard(Supermarket Admin) | Trang | Done | 3 | 2 | 1 | 2 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
1,64 | PB56 | [Test]Dashboard(Staff) | Thang | Done | 3 | 2 | 1 | 2 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
1,65 | PB57 | [Test]Dashboard(Charity) | Trang | Done | 3 | 4 | -1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1,66 | PB58 | [Test]Dashboard(Customer) | Binh | Done | 3 | 4 | -1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0
1,67 | PB59 | [Test]Dashboard(Delivery) | Bao | Done | 3 | 4 | -1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
1,68 | PB60 | [Test]Audit log | Huy | Done | 3 | 4 | -1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
1,69 | PB61 | [Test]Reports and analysis | Huy | Done | 3 | 3 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
1,70 |  | Sprint 3 Review Meeting | All member | Done | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
1,71 |  | Sprint 3 Retrospective | All member | Done | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
|  |  |  | Total | 345 | 342 | 3 | 346 | 1 | 6 | 20 | 12 | 16 | 16 | 18 | 18 | 19 | 15 | 17 | 21 | 19 | 22 | 7 | 22 | 22 | 14 | 6 | 29 | 20 | 6
|  |  |  | Burn down | [5 empty] | 340 | 320 | 308 | 292 | 276 | 258 | 240 | 221 | 206 | 189 | 168 | 149 | 127 | 120 | 98 | 76 | 62 | 56 | 27 | 7 | 1
|  |  |  | Burn up | [5 empty] | 6 | 26 | 38 | 54 | 70 | 88 | 106 | 125 | 140 | 157 | 178 | 197 | 219 | 226 | 248 | 270 | 284 | 290 | 319 | 339 | 345
|  |  |  | Hour/Day | 16.4286
|  |  |  | Estimate |  |  |  |  | 345 | 328.5714 | 312.1429 | 295.7143 | 279.2857 | 262.8571 | 246.4286 | 230 | 213.5714 | 197.1429 | 180.7143 | 164.2857 | 147.8571 | 131.4286 | 115 | 98.5714 | 82.1429 | 65.7143 | 49.2857 | 32.8571 | 16.4286 | 0
|  |  |  | Actual |  |  |  |  | 345 | 339 | 319 | 307 | 291 | 275 | 257 | 239 | 220 | 205 | 188 | 167 | 148 | 126 | 119 | 97 | 75 | 61 | 55 | 26 | 6 | 0
[9 empty] | Trang | 0 | 0 | 3 | 6 | 4 | 4 | 4 | 5 | 5 | 4 | 2 | 2 | 6 | 3 | 5 | 4 | 0 | 2 | 6 | 2 | 1 | 68
[9 empty] | Huy | 2 | 4 | 4 | 0 | 6 | 5 | 3 | 3 | 0 | 0 | 0 | 5 | 4 | 0 | 2 | 8 | 9 | 0 | 2 | 10 | 0 | 67
[9 empty] | Thang | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 2 | 4 | 7 | 10 | 8 | 8 | 2 | 2 | 0 | 0 | 1 | 7 | 0 | 0 | 59
[9 empty] | Binh | 0 | 4 | 5 | 6 | 1 | 7 | 9 | 7 | 2 | 4 | 5 | 2 | 2 | 0 | 5 | 5 | 4 | 0 | 9 | 5 | 0 | 82
[9 empty] | Bao | 0 | 0 | 0 | 2 | 3 | 2 | 2 | 2 | 4 | 2 | 4 | 2 | 2 | 2 | 8 | 5 | 1 | 3 | 5 | 3 | 1 | 53
Note on B7: ====== ID#AAABuu-MR1o jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAABuu-MR1w jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart

## Retrospective
Retrospective Log
Sprint # | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks
1 | Team leader | Apply git for version management and jira for work division. | Continue daily standup meetings on time, with clear goals | Do not change the sprint scope suddenly | Sprint completed on schedule
2 | Developer | Write more automated test cases for the search module | Maintain thorough code reviews before merging | Avoid letting many small bugs accumulate | Some errors were discovered late
3 | Tester | Enhance coordination between testers and developers when testing functions | Continue to use effective task management tools | Do not hold unnecessary meetings | Testers need more testing resources

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms | Sprint Backlog Template (Excel)
Official Scrum Guide | https://scrumguides.org/scrum-guide.html | Product Backlog
Scrum Alliance | : https://www.scrumalliance.org/
Mountain Goat Software (Mike Cohn) | https://www.mountaingoatsoftware.com/agile/scrum/sprint-backlog