International School

# Capstone Project 1

CMU-SE 450

PROJECT PLAN

Version 1.2

Date: December 12, 2025

LeafSense - Coffee Leaf Disease Detection System

Created by C1SE.03

Pham Minh Trang - 28204632177

Nguyen Pham Nhat Huy - 28211100686

Nguyen Huu Thang - 28211102537

Duong Quoc Binh - 28219006390

Nguyen Huy Hoang Bao - 28219004148

Project Plan Review Panel Representative:

Name					Signature		Date

Capstone Project 1 - Mentor:

Name MSc.Truong Dinh Huy	Signature		Date

PROJECT INFORMATION

| Project acronym | LeafSense |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Title | Coffee Leaf Disease Detection System |  |  |  |  |
| Start Date | September 8, 2025 | End Date |  | December 12, 2025 |  |
| Lead Institution | International School, Duy Tan University |  |  |  |  |
| Project Mentor | MSc.Truong Dinh Huy Email: huy.truongdinh@gmail.com Tel: 0982132352 |  |  |  |  |
| Scrum master / Project Leader & contact details | Pham Minh Trang Email: pmtrang04@gmail.com Tel: 0911855450 |  |  |  |  |
| Partner Organization | Duy Tan University |  |  |  |  |
| Team members | Name |  | Email |  | Tel |
| 28204632177 | Pham Minh Trang |  | pmtrang04@gmail.com |  | 0911855450 |
| 28211100686 | Nguyen Pham Nhat Huy |  | huy785619@gmail.com |  | 0395546300 |
| 28211102537 | Nguyen Huu Thang |  | nguyenhuuthang11@dtu.edu.vn |  | 0702377702 |
| 28219006390 | Duong Quoc Binh |  | duongquocbinh@dtu.edu.vn |  | 0932033856 |
| 28219004148 | Nguyen Huy Hoang Bao |  | bao91ndu1819@gmail.com |  | 0385092839 |

DOCUMENT APPROVALS

The following signatures are required for approval of this document.

| MSc.Truong Dinh Huy Mentor | Signature | Date |
| --- | --- | --- |
| Pham Minh Trang Student ID: 28204632177 Project Leader | Signature | Date |
| Nguyen Pham Nhat Huy Student ID: 28211100686 Team Member | Signature | Date |
| Nguyen Huu Thang Student ID: 28211102537 Team Member | Signature | Date |
| Duong Quoc Binh Student ID: 28219006390 Team Member | Signature | Date |
| Nguyen Huy Hoang Bao Student ID: 28219004148 Team Member | Signature | Date |

DOCUMENT NAME

| Document Title | Project Plan |  |  |
| --- | --- | --- | --- |
| Author(s) | Pham Minh Trang |  |  |
| Role | Product Owner, Team Member, Scrum Master |  |  |
| Date | December 12, 2025 | File name: | 02 C1SE.03_ Project Plan_ver1.2.doc |

REVISION HISTORY

| Version | Date | Comments | Author | Approval |
| --- | --- | --- | --- | --- |
| 1.0 | September 8, 2025 | Create Document | Trang |  |
| 1.1 | September 19, 2025 | Update Document | Trang |  |
| 1.2 | December 12, 2025 | Official Document | Trang |  |

Table of Contents

1. Introduction	1

1.1. Project Name	1

1.2. Project Duration	1

1.3. The Goal Of Project	1

1.4. Project Scope	2

2. Team Organize	3

2.1 Scrum Team Information	3

2.2. Roles And Responsibility	3

3. Schedules	4

3.1. Overall Schedules	4

3.2. Detail Schedules	5

4. Cost	6

4.1. Resources	6

4.2. Total Cost Estimate	6

5. Development Process	6

6. Development Environment	10

7. Communication & Reporting	11

7.1 Reporting Methodology	11

8. Risks	11

9. Deliverables	13

10. Configuration Management	13

11. References	14

# 1. Introduction

## 1.1. Project Name

The project’s name is: “LeafSense-Coffee Leaf Disease Detection System”

Team members:

- Pham Minh Trang	Scrum Master

- Nguyen Pham Nhat Huy	Product Owner

- Duong Quoc Binh	Team Member

- Nguyen Huu Thang                      Team Member

- Nguyen Huy Hoang Bao              Team Member

## 1.2. Project Duration

- Project will be started on: Aug – 18 – 2025

- Project will be finished on: Nov – 28 – 2025

## 1.3. The Goal Of Project

The goal of the project is to build an intelligent web-based system called “LeafSense – Coffee Leaf Disease Detection System” that helps coffee farmers detect and manage leaf diseases using artificial intelligence.

The project aims to:

- Enable users (farmers) to upload coffee leaf images for automatic AI-based disease detection and receive instant analysis results.

- Provide actionable recommendations for disease treatment and prevention, including pesticide suggestions, irrigation, and soil care methods.

- Integrate a chatbot assistant that can answer users’ questions about coffee care, disease symptoms, and system usage in real time.

- Offer a community platform where users can share experiences, post photos, comment, and interact.

- Include a marketplace that allows farmers to purchase agricultural products such as fertilizers or pesticides directly through the system.

- Ensure secure and efficient management for administrators, including user accounts, marketplace content, and community moderation.

- This project aims to enhance coffee production efficiency, reduce losses caused by late disease detection, and promote digital transformation in Vietnam’s agriculture.

## 1.4. Project Scope

This document provides an overview of the LeafSense – Coffee Leaf Disease Detection System, an intelligent web-based platform designed to assist coffee farmers in accurately identifying and managing leaf diseases using artificial intelligence.

The system enables users to upload coffee leaf images for AI-based disease detection and receive real-time diagnosis results along with treatment and prevention recommendations. It also integrates a chatbot assistant that answers users’ questions about disease symptoms, pesticide use, and general coffee care.

In addition, the system offers a community platform where farmers can share experiences, post comments, and exchange knowledge, as well as a marketplace that allows them to purchase agricultural products directly online. Administrators can efficiently manage user accounts, community content, and marketplace data through a secure backend system.

This document outlines the detailed planning and implementation of the LeafSense system, covering system architecture, feature integration, AI model development, and user experience optimization. It ensures a structured and practical approach to supporting digital transformation in agriculture and improving productivity for coffee farmers in Vietnam.

Languages and Technologies:
Python (FastAPI, PyTorch), JavaScript (ReactJS), HTML/CSS, MySQL

Duration: 14 weeks (18 August 2025 – 28 November 2025)

# 2. Team Organize

## 2.1 Scrum Team Information

Table 1. Scrum Team Information

| Full Name | Email | Phone number | Role |
| --- | --- | --- | --- |
| Pham Minh Trang | pmtrang04@gmail.com | 0911855450 | Scrum Master |
| Nguyen Pham Nhat Huy | huy785619@gmail.com | 0395546300 | Product Owner |
| Duong Quoc Binh | duongquocbinh@dtu.edu.vn | 0932033856 | Team member |
| Nguyen Huu Thang | nguyenhuuthang11@dtu.edu.vn | 0702377702 | Team member |
| Nguyen Huy Hoang Bao | bao91ndu1819@gmail.com | 0385092839 | Team member |

## 2.2. Roles And Responsibility

Table 2. Roles And Responsibility

| Role | Responsibility | Name |
| --- | --- | --- |
| Product Owner | - Understand the user and customers with their needs. - Collaborate with the development team. - Manage the stakeholders. - Describe the user experience and product features. - Provides detailed user stories. | Nguyen Pham Nhat Huy |
| Scrum Master | - Communicate the value of Scrum - Teach the organization on Scrum to maximize business value - Facilitate Sprint Planning, Daily Scrums, Sprint Reviews and Retrospective Meetings - Create the Task Board and Sprint Burndown Chart at the start of every Sprint - Attend all Scrum meetings - Preserve the integrity and spirit of the Scrum framework - Maintain the focus of the Team - Make the Team aware of impediments and facilitate efforts to resolve them - Serve as a coach and mentor to members of the Team - Respectfully hold the Team, Product Owner and Stakeholders accountable for their commitments - Continually work with the Team and business to find and implement improvements | Pham Minh Trang |
| Team member | Developer | All |
| Team member | Tester | Nguyen Huu Thang,Duong Quoc Binh, Nguyen Huy Hoang Bao |
| Team member | Designer | Pham Minh Trang |

# 3. Schedules

## 3.1. Overall Schedules

Table 3. Overall Schedules

| No | Phase | Iteration | Start Day | End Day |
| --- | --- | --- | --- | --- |
| 1 | Initial | Project Kick Off Meeting | August 18, 2025 | August 19, 2025 |
|  |  | Discuss about project idea | August 20, 2025 | August 22, 2025 |
| 2 | Development | Sprint 1 | September 08, 2025 | September 28, 2025 |
|  |  | Sprint 2 | October 06, 2025 | October 26, 2025 |
|  |  | Sprint 3 | November 03, 2025 | November 23, 2025 |
| 3 | Release | Project’s Meeting | November 24, 2025 | November 25, 2025 |
|  |  | Final release | November 26, 2025 | November 28, 2025 |

## 3.2. Detail Schedules

Table 4. Detail Schedules

| No. | Task Name | Start | Finish | Effort | Member |
| --- | --- | --- | --- | --- | --- |
| 1 | Initial | 18/08/2025 | 22/08/2025 | 40h | All |
| 1.1 | Project Kick Off Meeting, Discuss about project idea | 18/08/2025 | 19/8/2025 | 10h | All |
| 1.2 | Discuss project idea & define scope | 20/08/2025 | 22/08/2025 | 30h | All |
| 2 | Development | 08/09/2025 | 23/11/2025 | 1194h | All |
| 2.1 | Sprint 1 | 08/09/2025 | 28/09/2025 | 413h | All |
| 2.1.1 | Design, Code and Test the following Requirements/User Stories | 08/09/2025 | 26/09/2025 | 304h | All |
| 2.1.2 | Release Sprint 1 | 27/09/2025 | 28/09/2025 | 10h | All |
| 2.2 | Sprint 2 | 06/10/2025 | 26/10/2025 | 411h | All |
| 2.2.1 | Design, Code and Test the following Requirements/User Stories | 06/10/2025 | 24/10/2025 | 334h | All |
| 2.2.2 | Release Sprint 2 | 25/10/2025 | 26/10/2025 | 10h | All |
| 2.3 | Sprint 3 | 03/11/2025 | 23/11/2025 | 370h | All |
| 2.3.1 | Design, Code, and Test the following Requirements/User Stories | 03/11/2025 | 21/11/2025 | 321h | All |
| 2.3.2 | Release Sprint 3 | 22/11/2025 | 23/11/2025 | 10h | All |
| 3 | Release | 24/11/2025 | 28/11/2025 | 20h | All |
| 3.1 | Project Meeting | 24/11/2025 | 25/11/2025 | 10 | All |
| 3.2 | Final Release | 26/11/2025 | 28/11/2025 | 10 | All |

# 4. Cost

## 4.1. Resources

Table 5. Resources

| Full Name | Role | Salary Rate (USD / Hour) |
| --- | --- | --- |
| Pham Minh Trang | Scrum Master | 2.0 |
| Nguyen Pham Nhat Huy | Team Member | 2.0 |
| Duong Quoc Binh | Team Member | 2.0 |
| Nguyen Huu Thang | Team Member | 2.0 |
| Nguyen Huy Hoang Bao | Team Member | 2.0 |

## 4.2. Total Cost Estimate

The effort hours represent the total working hours of all team members combined.

Table 6. Total Cost Estimate

| Sprint | Duration(hours) | Cost ($) |
| --- | --- | --- |
| 1 | 413 | $826 |
| 2 | 411 | $822 |
| 3 | 370 | $740 |
| Total | 1194 | $2388 |

# 5. Development Process

- Principle and different stages

The SCRUM methodology is applied in this project because it best fits the nature of developing an AI-based agricultural web application that requires continuous feedback and frequent adjustments. LeafSense is developed incrementally and iteratively through three sprints (each lasting four weeks), ensuring that each iteration delivers a working version of the system with additional features and higher stability.

SCRUM emphasizes transparency and adaptability — the team maintains a Product Backlog that lists all system features and enhancements. Each sprint cycle includes planning, design, implementation, testing, and review activities. This approach helps the team quickly adapt to changes from mentor feedback or technical improvements to the AI model.

This method requires four types of meetings:

- Daily meetings: the entire team meets for approximately 15 minutes every day in order to answer the following three questions, usually while standing: what did I do yesterday? What am I going to do today? Is there a cumbersome impediment today?

- Planning meetings: the entire team gathers to decide on the features that will make up the following sprint.

- Work review meetings: during this meeting, every member presents what he has done during the sprint. They organize a demonstration of the new features or a presentation of the architecture. This is an informal meeting lasting for approximately 2 hours which is attended by the entire team.

- Retrospective meetings: at the end of each sprint, the team analyzes both successful and unsuccessful elements of their activity. During this meeting lasting between 15 and 30 minutes where everyone is invited and speaks on their behalf, a vote of confidence is organized to decide on the improvements to be made.

- The advantage of this method consists in reducing the documentation to the minimum to gain productivity. The idea is to write only the minimum documentation which allows for saving the history of the decisions taken on the project and easily performing interventions on the software when it goes into the maintenance phase.

- Agile - scrum organization

The SCRUM methodology involves the following three main players:

- Product owner: In most projects, the product owner is the leader of the client's project team. He is the one who will define and prioritize the product features and choose the date and content of each sprint based on the values (workloads) that the team communicates to him.

- Scrum Master: He is a genuine facilitator on the project as he makes sure that everyone works at their full potential by eliminating impediments and protecting the team from external interference. Moreover, he pays particular attention to the respect of the different SCRUM phases.

- Team: A team is typically made up of 4-10 people and groups together all the IT specialists who are necessary for a project, i.e. an architect, a designer, a developer, a tester, etc. The team is self-organizing and remains unchanged during an entire sprint.

Figure 1: Scrum team members.

- Agile - scrum advantages

Scrum differs from other development methods through its advantages which turn it into a pragmatic response to product owners' current needs:

- Iterative and incremental method: this allows to avoid the "tunnel effect", i.e. the fact of seeing the result only at the final delivery, and nothing or almost nothing during the entire development phase, which is so frequent with V-cycle developments.

- Maximum adaptability for product and application development: the sequential composition of the sprint content allows for the addition of a modification or a feature that was not initially planned. This is precisely what renders this method "agile".

- Participatory method: every team member is asked to express his opinions and can contribute to all the decisions taken on the project. He is therefore more involved and motivated.

- Enhancing communication: by working in the same development room or being connected through different communication means, the team can easily communicate and exchange opinions on the impediments to eliminate them as early as possible.

- Maximizing cooperation: daily communication between the client and the team enables them to collaborate more closely.

- Increasing productivity: as it removes certain "constraints" of the classical methods, such as documentation or exaggerated formalization, SCRUM allows for increased team productivity. By adding to this the qualification of each module which allows determining an estimation, everyone can compare their performance to the average team productivity.

- Risks and solutions

The SCRUM methodology does not offer a universal answer to all the problems that are inherent to software development. Teams need to pay attention to the risks below, which, nevertheless, offer a systematic answer based on extrapolating the method:

- Team size: team size is typically limited to 7 or 10 people and can become an impediment if it exceeds these recommendations. In the latter case, the organization of meetings becomes impossible and the very foundations of the method are affected. The solution is to set up a Scrum of Scrums. This consists in dividing the project into teams of appropriate sizes and adding an instance of a higher level which groups together the Scrum Master of each Scrum.

- Multiple requests: Requests may be transmitted through several channels on a project and can sometimes be difficult to manage due to their contradictory aspects. These contradictions can slow down the delivery validation process. In order to solve this problem, it is vital to use a single request management tool, which is a standard option for projects.

- Development quality: The more the number of teams increases, the more difficult it becomes to deal with quality. This rule is all the more true when the project is distributed among several centers. The main risks are related to code quality and the number of bugs identified during integration. This is why it is important to have a rigorous quality policy and a project quality plan that precisely defines the rules of the project. Frequent code audits and implementing indicators that measure the developers' performance allow for minimizing this risk.

# 6. Development Environment

Table 7. Development Environment

| Component | Development Environment |
| --- | --- |
| Operating system | - Windows |
| Development Tools | - Visual Studio Code (Frontend & Backend development) - MySQL Workbench (Database Management) - GitHub Desktop (Version Control) |
| Database | - MySQL |
| Client dependencies | - ReactJS 18.x - HTML5, CSS3, JavaScript (ES6) - Axios, Redux Toolkit (State Management) - Python: 3.9 |
| Server dependencies | - Python 3.9 - FastAPI Framework - SQLAlchemy ORM - Uvicorn Server - Pydantic (Schema Validation) |
| AI Model Environment | - Python 3.9 - YOLOv8 (Ultralytics) - OpenCV - Pandas, NumPy, scikit-learn - Google Colab for model training |
| Third-party dependencies | - Firebase Authentication (Login, Password Reset) - MoMo Payment Gateway (Online Payment) - Google Maps API (Delivery Location) - GitHub (Source Code Version Control) - Jira (Task & Sprint Management) - Zalo / Google Meet (Team Communication) |

# 7. Communication & Reporting

## 7.1 Reporting Methodology

Table 8. Reporting Methodology

| Audience/ Attendees | Topic/ Deliverable | Frequency | Method |
| --- | --- | --- | --- |
| - Product Owner - Scrum Master - Team Members | Project Progress Review | Weekly | Offline or Google Meet |
| - Product Owner - Scrum Master - Team Members | Explicit Requirement | When needed | Offline, Google Meet, Zalo |
| - Mentor - Scrum master - Team members | Milestone review | End of each Milestone | Offline |
| - Scrum master - Team members | Daily tasks | Each day | Google Meet, Zalo |

# 8. Risks

This part of the document contains several risks that could happen to the development team in the future. It also includes probability, severity, and mitigation strategies for each risk.

Table 9. Risks

| Risk | Definition | Probability | Severity | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Lack of coding experiences | Some members are not familiar with FastAPI, ReactJS, or YOLOv8 model training. | M | M | Conduct internal training sessions; share learning resources; pair programming to help each other quickly gain experience. |
| Source Code conflict | Problems while merging code between team members on GitHub repository. | H | L | Each member must pull the latest branch before committing, resolve merge conflicts locally, and review pull requests before merging to the main branch. |
| AI model performance issues | The trained model may not achieve expected accuracy or may overfit with the dataset. | M | H | Collect more diverse data, retrain the model, apply data augmentation, and evaluate metrics (Precision, Recall, F1-score). |
| Server or database failure | Backend or MySQL server may fail, causing downtime. | L | H | Use regular backups, versioned databases, and keep local copies of critical files. |
| Change the technology used. | Mentor feedback may lead to modifications or additional features (e.g., new chatbot functions). | M | M | Maintain flexible sprint planning and update backlog priority in Jira; hold short adjustment meetings if needed. |
| Time management | Members are also busy with work or university courses, leading to limited time for development. | H | M | Create a clear weekly schedule, divide tasks evenly, and work overtime when necessary before sprint deadlines. |
| Integration bugs between modules | AI, backend, and frontend may not work properly after integration. | M | M | Conduct integration testing at the end of each sprint; assign one member to verify API consistency and fix interface issues. |
| Communication breakdown | Misunderstanding tasks or sprint goals between members. | M | M | Hold daily updates on Zalo, document progress in Jira, and schedule weekly Google Meet review meetings. |

# 9. Deliverables

Table 10. Deliverables

| No | Activities | Deliverables |
| --- | --- | --- |
| 1 | Project Proposal | Document v1.2 |
| 2 | Project Plan | Document v1.2 |
| 3 | Product Backlog | Document v1.2 |

# 10. Configuration Management

Table 11. Configuration Management

| No. | Tool | Content |
| --- | --- | --- |
| 1 | Jira | Monitor and manage the progress of team members and sprint tasks. Create and track Product Backlog and Sprint Backlog, report bugs, assign tasks, and review progress each week.. |
| 2 | Google Drive | Archive all project documents. Change and manage the versions of each document. |
| 3 | GitHub | Store and manage the project repositories, manage branches, pull requests, and issues submitted by team members |
| 4 | Weekly Meetings | Hold a meeting every week to assign tasks to each member. |
| 5 | Document | All meetings and important updates must be recorded and stored (minutes, screenshots, and project logs). |
| 6 | Zalo | Communication tools for team members, storing discussion history and quick references related to tasks and technology. |
| 7 | Google Meet | Discuss online, stream, and share problems |

# 11. References

Table 12. List of References

| No. | References | Document Information |
| --- | --- | --- |
| 1 | Scrum Model | https://en.wikipedia.org/wiki/Scrum_(software_development) https://www.scrum.org/resources/scrum-guide https://www.atlassian.com/agile/scrum https://www.digite.com/agile/scrum-methodology/ |
| 2 | Agile Project Planning | https://www.atlassian.com/agile/project-management https://www.scrum.org/resources/what-is-agile |
| 3 | Software Project Management | https://www.tutorialspoint.com/software_project_management/index.htm |
| 4 | Risk Management in Software Projects | https://www.projectmanagement.com/articles/279800/Risk-Management-in-Agile-Projects https://www.atlassian.com/agile/project-management/risk-management |
| 5 | Software Development Life Cycle (SDLC) | https://www.tutorialspoint.com/sdlc/sdlc_overview.htm |