## Test report
Project Name | LeafSense - Coffee Leaf Disease Detection System
Stage | Sprint 1 |  |  | TOTAL | PASS | FAIL
Project Code |  |  | Status | 63 | 56 | 7
Test Environment Setup Description | Web |  | Re-test Status | 65 | 56 | 7
Tester | Pham Minh Trang
Nguyen Pham Nhat Huy
Duong Quoc Binh
Nguyen Huu Thang
Nguyen Huy Hoang Bao
Test Result | PASS
FAIL
SKIPPED
NOT IMPLEMENTED
No | Testcase ID | Function Name | Sheet Name | Create Date | End Date | Tester
1 | SU | Sign Up | Sign Up | Sep 13, 2025 | Sep 14, 2025 | Nguyen Huu Thang
2 | LI | Log In | Log In | Sep 13, 2025 | Sep 14, 2025 | Nguyen Pham Nhat Huy
3 | SG | Sign In with Google | Sign In with Google | Sep 13, 2025 | Sep 14, 2025 | Nguyen Huu Thang
4 | LO | Log Out | Log Out | Sep 13, 2025 | Sep 14, 2025 | Nguyen Huu Thang
5 | FP | Forgot Password | Forgot Password | Sep 14, 2025 | Sep 15, 2025 | Duong Quoc Binh
6 | HM | Home Page | Home Page | Sep 14, 2025 | Sep 15, 2025 | Nguyen Huu Thang
7 | PF-F | View Profile (Farmer) | View Profile (Farmer) | Sep 14, 2025 | Sep 15, 2025 | Nguyen Huy Hoang Bao
8 | PF-A | View Profile (Admin) | View Profile (Admin) | Sep 14, 2025 | Sep 15, 2025 | Nguyen Huy Hoang Bao

## Sign Up
Module |  | Sign Up
Code |  | SU
Check requirement
Tester |  | Pham Minh Trang
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 11 | 9 | 2 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 11 | 9 | 2 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Actual Result | Test Date | Status | Re-test Date | Re-test Status | Assign to
1 | SU - 1 | Sign Up | Check SignUp User Interface | none | 1. Go to the SignUp page | None | Show the same as UI design | Show the same as UI design | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
2 | SU - 2 | Sign Up | Enter valid data to login | none | 1. Go to the registration page 2. Enter email, password, confirm password, username, phone number and valid gender 3. Click the "Register" button | Username:"Thang04" Email: "thang04@gmail.com" Password: "thang04@" Confirm Password: "thang04@" | Show success message and redirect to main page | Show success message and redirect to main page | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
3 | SU - 3 | Sign Up | Invalid email entered | none | 1. Go to the registration page 2. Enter an incorrect email and other valid information 3. Click the "Register" button | Username:"Thang04" Email: "thang04gmail.com" Password: "thang04@" Confirm Password: "thang04@" | Show error "Email is not in correct format" | Show error "Email is not in correct format" | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
4 | SU - 4 | Sign Up | Enter weak password | none | 1. Go to the registration page 2. Enter a valid email, weak password and other valid information 3. Click the "Register" button | Username:"Thang04" Email: "thang04@gmail.com" Password: "0123456789" Confirm Password: "0123456789" | Show error "Password too weak" | Show: "Account Created Successfully" | Sep 15, 2025 | FAIL | Sep 24, 2025 | FAIL | Nguyen Huu Thang
5 | SU - 5 | Sign Up | Password and confirm password do not match | none | 1. Go to the registration page 2. Enter email, password and confirm different password, enter other valid information 3. Click the "Register" button | Username:"Thang04" Email: "thang04@gmail.com" Password: "thang05@" Confirm Password: "thang04@" | Show error "Password and confirm password do not match" | Show error " Password do not match" | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
6 | SU - 6 | Sign Up | Sign up with an existing email | none | 1. Go to the registration page 2. Enter an existing email in the system and other valid information 3. Click the "Register" button | Username:"Thang04" Email: "thang04@gmail.com" Password: "thang04@" Confirm Password: "thang04@" | Show error "Email already registered" |  | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
7 | SU - 7 | Sign Up | Check required fields | none | 1. Go to the registration page 2. Leave all fields blank 3. Click the "Register" button | none | Show error "Please fill in all required fields" |  | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
8 | SU - 8 | Sign Up | Check password length | none | 1. Go to the registration page 2. Enter a password shorter than the required length and other valid information 3. Click the "Register" button | Username:"Thang04" Email: "thang04@gmail.com" Password: "0123" Confirm Password: "0123" | Show error "Password must be at least 8 characters" | Show error "Password must be at least 8 characters" | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
9 | SU - 9 | Sign Up | Check that the password entered does not contain special characters | none | 1. Go to the registration page 2. Enter a password without special characters and other valid information 3. Click the "Register" button | Username:"Thang04" Email: "thang04@gmail.com" Password: "thang0411" Confirm Password: "thang0411" | Show error "Password must contain at least one special character" | Show: "Account Created Successfully" | Sep 15, 2025 | FAIL | Sep 24, 2025 | FAIL | Nguyen Huu Thang
10 | SU - 10 | Sign Up | Invalid email entered | none | 1. Go to the registration page 2. Enter an incorrect email and other valid information 3. Click the "Register" button | Username:"Thang04" Email: "thang04@@gmail.com" Password: "thang04@" Confirm Password: "thang04@" | Show error "Email is not in correct format" | Show error "Email is not in correct format" | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
11 | SU - 11 | Sign Up | Check the username field is empty | none | 1. Go to the registration page 2. Leave the username field blank and enter other valid information 3. Click the "Register" button | Username:"" Email: "thang04@gmail.com" Password: "thang04@" Confirm Password: "thang04@" | Show error "Username cannot be empty" | Show error "Username cannot be empty" | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang

## Log In
Module |  | Log In
Code |  | LI
Check requirement
Tester |  | Nguyen Pham Nhat Huy
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 11 | 11 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 11 | 11 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Actual Results | Test Date | Status | Re-test Date | Re-test Status | Assign to
1 | LI - 1 | Log In | Check User Interface | 1.On any page. 2. Click on the login button in the header. |  |  | Show same with UI design | Show same with UI design | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Pham Nhat Huy
2 | LI - 2 | Log In | Log in with the previously created account. | 1.On any page. 2. Click on the login button in the header. | 1. Enter Gmail in the Gmail field. 2. Enter the password in the password field. 3. Then click on the "Login" button. | Gmail : "thang04@gmail.com" Password : "thang04@" | Go to the home page with the logged-in status | Go to the home page with the logged-in status | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Pham Nhat Huy
3 | LI - 3 | Log In | Log in with an account that has not been previously created. | 1.On any page. 2. Click on the login button in the header. | 1. Enter Gmail in the Gmail field. 2. Enter the password in the password field. 3. Then click on the "Login" button. | Gmail : "thang045@gmail.com" Password : "thang04@" | Notification: This account does not exist. | Notification: Incorrect email or password! | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Pham Nhat Huy
4 | LI - 4 | Log In | Incorrect password entered during login. | 1.On any page. 2. Click on the login button in the header. | 1. Enter Gmail in the Gmail field. 2. Enter the password in the password field. 3. Then click on the "Login" button. | Gmail : "thang04@gmail.com" Password : "mksai123" | Notification: Incorrect password. | Notification: Incorrect email or password! | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Pham Nhat Huy
5 | LI - 5 | Log In | Log in with Google. | 1.On any page. 2. Click on the login button in the header. | 1. Click on the "Log in with Google" button. |  | Go to the home page with the logged-in status | Go to the home page with the logged-in status | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Pham Nhat Huy
6 | LI - 6 | Log In | Log in using Google with the previously logged-in Gmail account. | 1. Log in 2. The user is on the "myInfo" page | 1. Enter Gmail in the Gmail field. 2. Enter the password in the password field. 3. Then click on the "Login" button. | Gmail :"thang04@gmail.com" Password : "thang04@" | Notification: This Gmail account is already logged in when logging in with the Google account. | The system allows multiple concurrent logins with the same Google account. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Pham Nhat Huy
7 | LI - 7 | Log In | Log in using the username | 1. Log in 2. The user is on the "myInfo" page | 1. Click on the "Edit" button 2 . Select the full phone field 3 . Enter DATA 4. Click on the "Confirm" button | Gmail : "Thang04" Password : "thang04@" | Notification: You can only log in using Gmail. | Notification: The Gmail format is incorrect. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Pham Nhat Huy
8 | LI - 8 | Log In | Leave the Gmail field empty. | 1. Log in 2. The user is on the "myInfo" page | 1. Click on the "Edit" button 2 . Select the full phone field 3 . Enter DATA 4. Click on the "Confirm" button | Gmail : "" Password : "thang04@" | Notification: Gmail field cannot be empty. | Notification: Gmail field cannot be empty. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Pham Nhat Huy
9 | LI - 9 | Log In | Leave the password field empty. | 1. Log in 2. The user is on the "myInfo" page | 1. Click on the "Edit" button 2 . Select the full phone field 3 . Enter DATA 4. Click on the "Confirm" button | Gmail : "thang04@gmail.com" Password : "" | Notification: password field cannot be empty. | Notification: password field cannot be empty. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Pham Nhat Huy
10 | LI - 10 | Log In | Incorrect Gmail entered. | 1. Log in 2. The user is on the "myInfo" page | 1. Click on the "Edit" button 2 . Select the full phone field 3 . Enter DATA 4. Click on the "Confirm" button | Gmail : "thangg044@gmail.com" Password : thang04@" | Notification: Gmail does not exist. | Notification: Gmail does not exist. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Pham Nhat Huy
11 | LI - 11 | Log In | Leave both the Gmail and password fields empty. | 1. Log in 2. The user is on the "myInfo" page | 1. Click on the "Edit" button 2 . Select the full phone field 3 . Enter DATA 4. Click on the "Confirm" button | Gmail : "" Password : "" | Notification: Please enter your Gmail and password. | Notification: Please enter your Gmail. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Pham Nhat Huy

## Sign In with Google
Module |  | Sign In with Google
Code |  | SG
Check requirement
Tester |  | Nguyen Huu Thang
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 10 | 9 | 1 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 10 | 9 | 1 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Actual Results | Test Date | Status | Re-test Date | Re-test Status | Assign to
1 | SG - 1 | Sign In with Google | Verify “Sign in with Google” button appears on Sign In page | 1. User is not logged in. 2. Google Sign-In feature enabled in system settings. 3. Stable internet connection. | 1. Open application. 2. Navigate to Sign In page. 3. Observe login options. | None | “Sign in with Google” button is visible and clickable. | “Sign in with Google” button is visible and clickable. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
2 | SG - 2 | Sign In with Google | Verify system redirects user to Google login page | 1. User is on Sign In page. 2. Google Sign-In enabled. | 1. Click “Sign in with Google”. | None | User is redirected to Google authentication screen. | User is redirected to Google authentication screen. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
3 | SG - 3 | Sign In with Google | Verify user can sign in using a valid Google account | 1. User has a valid Google account. 2. Google account is not blocked. | 1. Click “Sign in with Google”. 2. Select Google account. 3. Grant required permissions. | Valid Google account | User is logged in successfully and redirected to homepage/dashboard. | User is logged in successfully and redirected to homepage/dashboard. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
4 | SG - 4 | Sign In with Google | Verify system creates new user account for first-time Google login | 1. Google account email does not exist in system database. | 1. Sign in using Google for the first time. 2. Complete authentication. | New Google account | New user account is created automatically and logged in. | New user account is created automatically and logged in. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
5 | SG - 5 | Sign In with Google | Prevent duplicate accounts for existing email | 1. User email already exists in system. 2. Email matches Google account email. | 1. Click “Sign in with Google”. 2. Login using existing Google account. | Existing Google account | User logged in to existing account, no duplicate created. | User logged in to existing account, no duplicate created. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
6 | SG - 6 | Sign In with Google | Verify system handles user canceling Google login | 1. User redirected to Google login page. | 1. Click “Cancel” or close Google authentication window. | None | User is returned to Sign In page without being logged in. | Clicking on "Log in with Google" takes you to the login page without a cancel button. | Sep 15, 2025 | FAIL | Sep 24, 2025 | FAIL | Nguyen Huu Thang
7 | SG - 7 | Sign In with Google | Verify system handles Google service downtime | 1. User is on the Sign In page. 2. Google Sign-In feature is enabled. 3. Internet connection is initially available. | 1. Click the “Sign in with Google” button. 2. While redirecting to Google authentication page, disconnect the Internet connection (turn off Wi-Fi/mobile data). 3. Wait for system response. | None | System displays a network-related error message (e.g., “Internet connection lost. Please try again.”). User is not logged in. | System displays a network-related error message (e.g., “Internet connection lost. Please try again.”). User is not logged in. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
8 | SG - 8 | Sign In with Google | Verify system retrieves basic user info from Google | 1. Google login successful. | 1. Login using Google. 2. Open user profile page. | None | Email, name, and profile picture (if available) are populated correctly. | Email, name, and profile picture (if available) are populated correctly. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
9 | SG - 9 | Sign In with Google | Ensure locked accounts cannot access system via Google | 1. User account is locked by admin. 2. Google account email matches locke | 1. Click “Sign in with Google”. 2. Complete Google authentication. | Locked Google account | Login is blocked with message “Account is locked”. | Login is blocked with message “Account is locked”. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang
10 | SG - 10 | Sign In with Google | Verify login session is created correctly | 1. User logged in via Google successfully. | 1. Refresh browser. 2. Navigate to another page. | None | User remains logged in; no re-login required. | User remains logged in; no re-login required. | Sep 15, 2025 | PASS | Sep 24, 2025 | PASS | Nguyen Huu Thang

## Log Out
Module |  | Log Out
Code |  | LO
Check requirement
Tester |  | Nguyen Huu Thang
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 6 | 4 | 2 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 6 | 4 | 2 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Actual Result | Test Date | Status | Re-test Date | Re-test Status | Assign to
1 | LO - 1 | Log Out | Check logout from main page | User is logged in | 1. On the Home page, click on the current administrator account 2. Click Log Out | None | User is logged out and redirected to login page | User is logged out and redirected to login page | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang
2 | LO - 2 | Log Out | Verify user cannot access dashboard after logout | User has logged out | 1. Logout successfully 2. Enter dashboard URL | /dashboard | System redirects user to login page | User is still able to access the dashboard page by entering the URL directly after logging out. | Sep 16, 2025 | FAIL | Sep 25, 2025 | FAIL | Nguyen Huu Thang
3 | LO - 3 | Log Out | Verify session is cleared after logout | User has logged out | 1. Logout successfully 2. Refresh browser | None | User remains on login page and is not logged in | User remains on login page and is not logged in again | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang
4 | LO - 4 | Log Out | Logout on one browser while logged in on another browser | User logged in on two browsers | 1. Logout on Browser A 2. Check session on Browser B | Same account | User on Browser A is logged out; Browser B session remains active | User on Browser A is logged out; Browser B session remains active | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang
5 | LO - 5 | Log Out | Verify user cannot access previous page using browser Back button | User has logged out | 1. Logout successfully 2. Click browser Back button | None | User stays on login page | User stays on login page | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang
6 | LO - 6 | Log Out | Verify session is cleared after logout and browser close | User is logged in | 1. Logout successfully 2. Close browser 3. Open browser again and access dashboard | /dashboard | User is redirected to login page | User is still able to access the dashboard page by entering the URL directly after logging out. | Sep 16, 2025 | FAIL | Sep 25, 2025 | FAIL | Nguyen Huu Thang

## Forget Password
Module |  | Reset Password
Code |  | RP
Check requirement
Tester |  | Nguyen Huu Thang
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 8 | 8 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 8 | 8 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Actual Result | Test Date | Status | Re-test Date | Re-test Status | Assign to
1 | RP - 1 | Forgot Password | Check User Interface | None | 1. Access Login Page 2. Click “Forgot Password” link | None | Show “Forgot Password” page with email input box and “Send” button | Show “Forgot Password” page with email input box and “Send” button | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang
2 | RP - 2 | Forgot Password | Send reset email successfully | None | 1. Access “Forgot Password” page 2. Enter registered email 3. Click “Send” button | Email = “thang04@gmail.com | Show “Forgot Password” page with email input box and “Send” button | Show “Forgot Password” page with email input box and “Send” button | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang
3 | RP - 3 | Forgot Password | Send reset email failed with unregistered email | None | 1. Access “Forgot Password” page 2. Enter unregistered email 3. Click “Send” button | Email = “thang044@email.com” | Notification: “Email not found” | Show “Forgot Password” page with email input box and “Send” button | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang
4 | RP - 4 | Forgot Password | Send reset email failed when email is empty | None | 1. Access “Forgot Password” page 2. Leave email empty 3. Click “Send” button | Email = “” | Notification: “Email is required” | Notification: “Email is required” | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang
5 | RP - 5 | Forgot Password | Check valid reset link | User received reset email | 1. Open email inbox 2. Click “Reset Password” link in email | Valid link | Redirect to “Reset Password” page | Redirect to “Reset Password” page | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang
6 | RP - 6 | Forgot Password | Reset password failed when confirm password does not match | User opened valid reset link | 1. Enter new password and confirm password 2. Click “Confirm” button | New Password = “thang04@” Confirm Password = “thang044@” | Notification: “Passwords do not match” | Notification: “Passwords do not match” | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang
7 | RP - 7 | Forgot Password | Reset password successfully | User opened valid reset link | 1. Enter new password and confirm password 2. Click “Confirm” button | New Password = “thang04@” Confirm Password = “thang04@” | Notification: “Password reset successfully” | Notification: “Password reset successfully” | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang
8 | RP - 8 | Forgot Password | Reset password failed when new password is empty | User opened valid reset link | 1. Leave new password empty 2. Click “Confirm” button | New Password = “” Confirm Password = “” | Notification: “All fields are required” | Notification: “All fields are required” | Sep 16, 2025 | PASS | Sep 25, 2025 | PASS | Nguyen Huu Thang

## Home Page
Module |  | Home Page
Code |  | HM
Check requirement
Tester |  | Nguyen Huu Thang
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 7 | 7 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 9 | 7 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Actual Result | Test Date | Status | Re-test Date | Re-test Status | Assign to
1 | HM - 1 | Home Page | Verify that the Home Page loads successfully | 1. User has a valid account 2. System is running | 1. Open browser 2. Navigate to system URL | None | Home Page is displayed correctly without errors | Home Page is displayed correctly without errors | Sep 17, 2025 | PASS | Sep 26, 2025 | PASS | Nguyen Huu Thang
2 | HM - 2 | Home Page | Verify navigation bar is displayed correctly | User is logged in | 1. Open Home Page | None | Navigation bar displays correct menu items (Dashboard, Upload, History, Marketplace, etc.) | Navigation bar displays correct menu items (Dashboard, Upload, History, Marketplace, etc.) | Sep 17, 2025 | PASS | Sep 26, 2025 | PASS | Nguyen Huu Thang
3 | HM - 3 | Home Page | Verify user info is shown on sidebar | User is logged in | 1. Open Home Page 2. Check sidebar at bottom | None | User’s name, email, and avatar appear correctly | User’s name, email, and avatar appear correctly | Sep 17, 2025 | PASS | Sep 26, 2025 | PASS | Nguyen Huu Thang
4 | HM - 4 | Home Page | Verify “Log Out” button functionality | User is logged in | 1. Click “Log Out” button | None | System logs out successfully and redirects to Login Page | System logs out successfully and redirects to Login Page | Sep 17, 2025 | PASS | Sep 26, 2025 | PASS | Nguyen Huu Thang
5 | HM - 5 | Home Page | Verify error handling when backend is unavailable | Backend server is stopped | 1. Refresh Home Page | None | System shows friendly error message “Unable to connect to server” | System shows friendly error message “Unable to connect to server” | Sep 17, 2025 | PASS | Sep 26, 2025 | PASS | Nguyen Huu Thang
6 | HM - 6 | Home Page | Verify Home Page performance | User has stable internet | 1. Open Home Page | None | Page loads fully within 3 seconds | Page loads fully within 3 seconds | Sep 17, 2025 | PASS | Sep 26, 2025 | PASS | Nguyen Huu Thang
7 | HM - 7 | Home Page | Verify Home Page UI consistency | User is logged in | 1. Observe layout, colors, and spacing | None | All UI elements align properly, consistent with design | All UI elements align properly, consistent with design | Sep 17, 2025 | PASS | Sep 26, 2025 | PASS | Nguyen Huu Thang

## View Profile(User)
Module |  | View Profile (User)
Code |  | VP
Check requirement
Tester |  | Nguyen Huy Hoang Bao
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 2 | 2 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 2 | 2 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Actual Result | Test Date | Status | Re-test Date | Re-test Status | Assign to
1 | VP - 1 | View Profile (User) | Check if the user profile information is displayed correctly. | 1. Logged 2..Has a profile in the database | 1. Log in to the system. 2. Access the user profile section. | None | Display complete and accurate profile information, including name, encrypted email, gender, user type, and formatted phone number. | Display complete and accurate profile information, including name, encrypted email, gender, user type, and formatted phone number. | Sep 18, 2025 | PASS | Sep 27, 2025 | PASS | Nguyen Huy Hoang Bao
2 | VP - 2 | View Profile (User) | Check the display of user avatar | 1. The user has logged 2. Access the user profile section. | 1. Log in to the system. 2. Access the "Profile" page. | None | The user's avatar is displayed correctly and without errors. | The user's avatar is displayed correctly and without errors. | Sep 18, 2025 | PASS | Sep 27, 2025 | PASS | Nguyen Huy Hoang Bao

## View Profile(Admin)
Module |  | View Profile (Admin)
Code |  | AP
Check requirement
Tester |  | Nguyen Huy Hoang Bao
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 8 | 6 | 2 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 8 | 6 | 2 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Actual Result | Test Date | Status | Re-test Date | Re-test Status | Assign to
1 | AP - 1 | View Profile (Admin) | Verify that the “View Profile” button is visible on the Dashboard | Admin is logged into the system | 1. Log in as Admin 2. Open Dashboard page | None | “View Profile” button or menu is clearly visible | “View Profile” button or menu is clearly visible | Sep 18, 2025 | PASS | Sep 27, 2025 | PASS | Nguyen Huy Hoang Bao
2 | AP - 2 | View Profile (Admin) | Verify that clicking “View Profile” opens the profile page | Admin is logged in | 1. Click on “View Profile” | None | The “Admin Profile” page opens and displays admin details | The “Admin Profile” page opens and displays admin details | Sep 18, 2025 | PASS | Sep 27, 2025 | PASS | Nguyen Huy Hoang Bao
3 | AP - 3 | View Profile (Admin) | Verify that profile information is displayed correctly | Admin has valid information in the database | 1. Open “Admin Profile” page | None | Fields such as Full Name, Email, Role (Admin), and Avatar are displayed accurately | Fields such as Full Name, Email, Role (Admin), and Avatar are displayed accurately | Sep 18, 2025 | PASS | Sep 27, 2025 | PASS | Nguyen Huy Hoang Bao
4 | AP - 4 | View Profile (Admin) | Verify that the “Edit Profile” button is displayed | Admin is on the Profile page | 1. Open “Profile” page | None | “Edit Profile” button is visible and clickable | “Edit Profile” button is visible and clickable | Sep 18, 2025 | PASS | Sep 27, 2025 | PASS | Nguyen Huy Hoang Bao
5 | AP - 5 | View Profile (Admin) | Verify that admin can successfully edit and save profile information | Admin is on the Profile page | 1. Click “Edit Profile” 2. Change display name 3. Click “Save” | New Name: “Admin LeafSense” | System saves changes and shows success message “Profile updated successfully” | System saves changes and shows success message “Profile updated successfully” | Sep 18, 2025 | PASS | Sep 27, 2025 | PASS | Nguyen Huy Hoang Bao
6 | AP - 6 | View Profile (Admin) | Verify saving without making any changes | Admin is on the Profile page | 1. Click “Edit Profile” 2. Make no changes 3. Click “Save” | None | System displays message “No changes were made” | System saves changes and shows success message “Profile updated successfully” | Sep 18, 2025 | FAIL | Sep 27, 2025 | FAIL | Nguyen Huy Hoang Bao
7 | AP - 7 | View Profile (Admin) | Verify that “Back to Dashboard” button works properly | Admin is on the Profile page | 1. Click “Back to Dashboard” | None | System redirects back to the Admin Dashboard | System redirects back to the Admin Dashboard | Sep 18, 2025 | PASS | Sep 27, 2025 | PASS | Nguyen Huy Hoang Bao
8 | AP - 8 | View Profile (Admin) | Verify error handling when saving profile with lost connection | Internet connection is lost | 1. Click “Edit Profile” 2. Change email 3. Click “Save” | newadmin@gmail.com | System shows error message “Unable to save. Please check your connection.” | System saves changes and shows success message “Profile updated successfully” | Sep 18, 2025 | FAIL | Sep 27, 2025 | FAIL | Nguyen Huy Hoang Bao